## RA Worksheet
Risk Assessment Worksheet |  |  |  | 1. Project/Incident/Work Activity |  |  | 2. Location
|  |  |  | Air Tanker and Seat Base Operations |  |  | Cedar City, Richfield, Fillmore or any other Airstrip where a Seat Base is Established
3. Specific Objective |  |  |  | 4. Name and Title of Preparer |  |  | 5. Date
To provide a safe and efficient work environment for flight crews and tanker base personnel while supporting fire suppression activities. |  |  |  | Clint Coates, Forest Aviation Officer |  |  | 2022-03-17
6. Risk Decision Authority: (Authority Signature Block) If block 15 is Moderate, High or Extremely High a higher level of authority needs to sign in this block.
Signature/Date:
Assess Hazards |  |  |  |  | Identify Risk Mitigation Measures | Residual Risk
7. Task | 8. Hazard | 9. Severity/ Consequence | 10. Hazard Probability | 11. RAC | 12. List all mitigation or abatement measures | 13. Severity/ Consequences | 14. Hazard Probability | 15. RAC | 16. Necessary (Yes/No) | 17. Hazard Control Assigned to:
Loading / Parking Aircraft | Personnel not qualified or familiar with equipment. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Ensure personnel are fully qualified and current with refresher training and certification in assigned position. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Loading / Parking Aircraft | Slick Ramp (Oil & Retardant) | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Limit spills, use a bucket under fill port to catch retardant, wash down area if spillage occurs, absorb oil with absorbent material, and wear good traction footwear. Airtankers with leaking doors will not be cleared for engine startup until leaks are stopped. Clean the ramp at the end of each major fire activity and at the end of the season to reduce the chance of aircraft skids or personnel slips due to accumulations of oil or retardant leakage. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Loading / Parking Aircraft | High Noise Levels | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Wear approved hearing protection. Provide appropriate hearing protection. Review “Hearing Safety at ATB’s”. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Loading / Parking Aircraft | Flying Debris from prop wash, retardant or oil going into eyes | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Wear eye protection. Avoid areas of severe prop wash. Secure loose items on ramp or move them off the ramp to prevent them from being caught in propeller wash. If blinded kneel to ground and wait. Do not try move without vision. Communicate your situation to others. Provide proper eye protection and eye wash station and showers. Do not allow spectators to get near startup, run up, and takeoff areas. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Loading / Parking Aircraft | Sunburns Heat Stress | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Use Sun Screen. Wear clothes that help keep cool. See ground crew fatigue below. Provide shade, drinking water, and rotate personnel. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Loading / Parking Aircraft | Tripping | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Remove all tripping hazards and identify and Mark all un-moveable hazards. Remove tripping hazards and Mark un-moveable hazards. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Loading / Parking Aircraft | Being run over by airplane or prop-strike. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Only required personnel on the ramp. Parking tenders will wear a bright colored vest and be trained. Loading crew will remain at the retardant tanks until all engines have stopped. Parking tenders will have communication with the pilots (radio or hand signals) and clear all engine startups. No engine will be started until loaders are clear of the area and a visual check has been made for unsecured equipment or materials, leaking doors, missing filler caps or vent plugs, and anything unusual. Personnel will keep clear of the prop arc even when engines are off. All fixtures within 20 ft. of the edge of the ramp shall be less than 5 ½ feet in height above the ramp surface. In passenger or air cargo operations, vehicles and personnel shall remain clear of the ramp until all propellers come to a complete stop and the aircraft parking tender signals them to approach. All passengers will be escorted by a qualified marshaler who will keep between the passengers and the prop. If an outboard engine is kept running, a second marshaler shall be used to prevent anyone from approaching the area of the running engine. Provide training and appropriate PPE for ramp personnel. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Loading / Parking Aircraft | Wing-strike | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Move aircraft parked too close to the taxiway or ground servicing vehicles parked within 100 ft. of the taxiway centerline. Use wing walkers and nose spotters to advise the aircraft parking tender when clearances are tight. Consult with the Airport Manager on any obstacles that appear to penetrate airfield obstacle free areas. Any item over 8 ft. in height within 60 ft. of the ramp will not be left unattended when aircraft are passing by. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Loading / Parking Aircraft | Sudden settling of an aircraft gear strut | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Avoid work/loading directly under the wing. Stand at the manifold valve. Keep knees slightly bent if avoidance is not possible. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Parking Aircraft | Night parking | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Use lighted signal wands and additional spotters. Provide Signal wands and adequate numbers of spotters. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Loading / Parking Aircraft | Aircraft Fire | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Parking tender will notify the pilot (radio or hand signal) All ramp personnel will evacuate. Notify Base Operations (radio or phone). Fire extinguishers will be available at each pit for aircrew use. Notify dispatch to call 911 if fire cannot be extinguished. Have fire extinguishers located adjacent to loading pits and parking areas. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Loading / Parking Aircraft | Stack fires/brake fires | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | The parking tender or ramp manager will provide a fire watch for each engine startup within the ramp area. Signal the flight crew for fuel flowing from the drain in the event of an over-primed engine. Signal the flight crew in the event of a stack fire. Pilots will usually start the engine to stop a stack fire. Direct aircraft with hot or smoking brakes away from the loading ramp. Call 911 in the case of a brake fire that does not go out. Monitor Aircraft during approach and departure from parking area or pits. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Pilots RAMP manager and Parking Tenders
Fueling Aircraft | Fuel fire on the ramp | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Smoking is prohibited within 50 ft. of an aircraft and 100 ft. of a fueling operation. All agency personnel must be at least 50 ft. from any fueling aircraft. Simultaneous fueling and loading of retardant is permitted at bases that allow it as long as it is done following Simultaneous Loading/Fueling plan. Hot refueling (fueling while engines are running is not permitted except in helicopters authorized to perform rapid refueling. Fueling will be supervised by qualified agency personnel to assure that procedures such as bonding are done. All fueling is prohibited when electrical storms are within 2 miles of the base. In the event of a fire, the ATBM will notify the fire department via 911. Also he will notify the Airport Manager. Evacuate the ramp and plant area. Dry chemical fire extinguishers (125 lb.) are furnished at each loading pit for use by trained personnel. Refer to the Base Emergency Plan for greater detail. Monitor fueling operations from a safe distance. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders, Fuelers
Fueling Aircraft | Fuel Spill | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Follow established fueling procedures. Eliminate any ignition sources and clear ramp area of unnecessary personnel. Wash spilled fuel to drains, which lead to the pond. Use absorbent booms in pond to soak up spilled fuel. Dispose of booms in accordance with guidelines. Ensure the contractor is following the spill guidelines in the contract. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Contractor, Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders, Fuelers
Parking Aircraft | Offsite parking of large aircraft | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Offsite parking must be preplanned and prearranged with the Airport Manager to ensure sufficient weight bearing capability and to prevent conflicts with other users. Areas to be used will require inspection before utilization for subsurface cavitation, FOD, or any changed condition. Pre-marking of parking pads may be required to ensure adequate spacing and procedural safety. Provide for adequate security. Large aircraft can draw spectators. Provide personnel to guide spectators and protect aircraft when offsite parking is such that spectators are attracted to the site. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Contractor, Pilots, Aircraft Managers, Tanker Base Manager or Asst. Tanker Base Manager RAMP manager and Parking Tenders
Loading / Parking Aircraft | Ground crew fatigue | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Limit exposure to excessive heat, noise, wind, and dust. Rotate crews. Provide standby room and drinks and high-energy food as appropriate. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Tanker Base Manager RAMP manager and Parking Tenders
Loading Aircraft | Hot loading | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Only when authorized. Must be trained and follow established procedures. Provide necessary training to employees involved in hot load procedures. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Contractor, Tanker Base Manager, RAMP manager and Parking Tenders
Base Operations | Fork Lift Operations | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Only trained and authorized personnel shall operate forklifts. All applicable PPE and safety precautions shall be observed. Provide necessary training to employees | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Base Operations | Thunderstorms/Lightning | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | All persons shall be removed from the ramp area in the event of a thunderstorm. Terminate any fueling and loading operations until the storm has passed. Monitor Weather both visual and radar systems and take appropriate actions if inclement weather looks imminent. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Rare | Moderate | Yes | UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Base Operations | Chemical spills | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Store hazardous materials in hazardous materials storage containers/ bins. Clean up small spills in accordance with procedures. Large spills will require notification and coordination with HazMat coordinator. Follow mitigation procedures outlined in the MSDS for materials. Follow procedures outlines in the Hazardous Communication Plan when needed. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Contractor, Tanker Base Manager RAMP manager and Parking Tender
Loading Aircraft | Blown retardant hose | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Inspect loading hoses at the beginning of each season. Exposure to sunlight and over pressuring the loading hose causes the hose to weaken. Closing the manifold valve on the aircraft before shutting down the retardant pump causes overpressure damage. Inspect the hose sheath, clamps, and cord regularly. Train loading personnel on correct procedures. Routinely inspect and replace worn or damaged hoses | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Contractor, Tanker Base Manager, RAMP manager and Parking Tender
Base Operations | Potential unsafe flight conditions | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Pilot in command (PIC) is responsible for the safety of the aircraft, cargo, and occupants. PIC has complete authority to postpone, change, or cancel their flight when they believe existing or impending conditions make it unsafe. Air tanker base manager will terminate or cancel air base operations when conditions make operations abnormally hazardous or when pilot does not adhere to essential precautionary measures. Monitor condition of environment, flight crew, aircraft and situation to determine if flight will be safe. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Pilots, ATGS, UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager, RAMP manager and Parking Tender
Flight Operations | Unqualified pilots and aircraft | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Verify pilot and aircraft cards | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Rare | Low | Yes | Aircraft Managers
Flight Operations | Fixed aerial hazards, military training routes, & other a/c assigned to fires | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Provide pilots a copy of the resource order, brief pilots on other aircraft assigned to incident, on any known aerial hazards, on military training routes, and display aerial hazard maps. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Pilots, ATGS, UAM, FAO, Aircraft managers
Flight Operations | Aborted loads of retardant | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Keep spectators away from departure paths. Brief pilot and copilot of jettison areas. Emergency jettison shall be over uninhabited areas at altitudes > 2000 AGL if possible. Advise callers to wash retardant off houses and cars as soon as possible to prevent damage to paint. Wash exposed skin and clothes. Retardant is not toxic but can be a skin irritant. Follow Jettison protocol and communicate to dispatch and any ground personnel affected. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Flight Operations/ Airport Runways | Foreign Object Debris (FOD) | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Complete FOD walks daily of the ramp area. Be cognizant of any FOD that may be aircraft parts. Pickup all foreign debris daily | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Tanker Base Manager or Assistant Tanker Base Manager, RAMP manager and Parking Tender
Flight Operations/ Airport and Ramp | Aircraft ground collision | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | All aircraft will be assigned a trained parking tender. Wing walkers will be used when necessary. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Rare | Moderate | Yes | Tanker Base Manager or Assistant Tanker Base Manager, RAMP manager and Parking Tender
Flight Operations | Flight crew fatigue | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Provide standby facility, timely lunches to all air crews (during on-going fires), and drinks. Enforce duty limits as specified in Airtanker Contract. Watch for Phase II and Phase III flight & duty limitations. Talk with Flight Crews and tanker bas personnel to identify fatigue before problems occur | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Pilots, ATGS, UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager, RAMP manager and Parking Tender
Loading / Parking Aircraft | Overloading aircraft | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Loading crew will verify the pounds of retardant loaded onto the aircraft using the load holes or on board systems. A manifest will be prepared for passenger carrying aircraft. The manifest will document passenger and cargo weights. Retain a copy of the manifest in dispatch. The northwest end of the air center is the passenger/cargo processing and weighing area. Load calculations will be completed for helicopters. Prepare Manifests and communicate payloads to loading personnel | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Rare | Moderate | Yes | Contractors, Tanker Base Manager and Aircraft Managers
Base Operations/Flight Operations | Transportation of hazardous materials | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Fixed wing must follow Department of Transportation regulations for the transport of hazardous materials. Helicopters going directly to the field may use the interagency hazardous materials guide. Adhere to Hazmat Policies | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Rare | Moderate | Yes | UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager, and Aircraft Managers
Base Operations/Flight Operations | Airport congestion/ Flight Traffic Congestion | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Request ATGS and TFR as deemed appropriate to congestion problem. Monitor 122.9 MHz for civilian aircraft in flight. Airtankers will contact the base within 5 minutes of landing on RAMP or LOCAL FF for a secondary fallback frequency. Monitor Unicom for other airport traffic. Parking tenders be observant of other aircraft especially when tanker is on final. Request temporary FAA control tower if conditions warrant. Adhere to “Sterile Cockpit” procedures when aircraft are in local airport approach or departure traffic pattern. Utilize TFR for fires utilizing numerous aircraft Monitor correct frequencies and communicate aircraft intentions | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Rare | Moderate | Yes | Pilots, ATGS, UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager, RAMP manager and Parking Tender
Flight Operations | Airport congestion exceeding 25 takeoffs/landings per hr | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Consider requesting a temporary FAA control tower. Coordinate with Airport Manager to determine FAA temp tower needs. Coordinate with Airport Manager to determine FAA temp tower needs | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Rare | Low | Yes | Pilots, ATGS, UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Flight Operations | Aircraft attempting to land while another is attempting takeoff | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Unlikely | High | Monitor approaching and departing aircraft. Monitor Unicom to see if communication between aircraft has been established. Contact one of the aircraft if in doubt. | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Rare | Moderate | Yes | Pilots, ATGS, UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Flight Operations | Landing and departure vortices from heavy aircraft when wind is straight down the runway. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Provide adequate separation between take offs . Monitor Unicom to inform light aircraft attempting to land or takeoff too closely behind an airtanker are informed of the hazard. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Rare | Moderate | Yes | Pilots, ATGS, UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Flight Operations/ Environmental | “Brownout” due to dust from initial gusts of a thunder cell at airport. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Relay to pilots in flight. Do not clear aircraft on the ground to start engines until the “wall” has passed. Monitor conditions and communicate hazards | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Rare | Moderate | Yes | Pilots, ATGS, UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Flight Operations/ Base Operations | Dust devils or microbursts in vicinity of the airport. Dust devils and or winds exceeding 30 mph at airport | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Relay information to pilots in flight. Tie down light aircraft. Request contractors stabilize control surfaces on large aircraft such as rudders if that is company procedure. Some a/c such as turbine engine aircraft may require parking with nose into the wind. Monitor Weather both visual and radar systems and take appropriate actions if inclement weather looks imminent. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Flight Operations/ Environmental | Smoke reduced visibility under 5 mi. at airport or between airport and Fire | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | If situation appears that it will persist such as extended grass field burning or other large wildfires, consider temp. FAA tower. Discuss situation with ATGS or individual pilots if no ATGS. Relay information to any aircraft already in flight. Monitor Visibility both ocular and AWOS to maintain awareness of current conditions. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Pilots, ATGS, UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Flight Operations | Military intercept | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Unlikely | High | Monitor and respond on 121.5 MHz Coordinate with Military controls to know if military routes are active. | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Rare | Moderate | Yes | Dispatch, Pilots, ATGS, UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Flight Operations | Overdue/missing aircraft | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Unlikely | High | Follow procedures established for flight following. Use Forest Aviation Incident/Accident Response Guide when aircraft becomes overdue or missing. Initiate overdue aircraft protocol. | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Rare | Moderate | Yes | Dispatch, UAM, FAO, Aircraft Managers
Flight Operations/ Base Operations | Long distance dispatches | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Download retardant to provide for sufficient fuel. Do not load retardant if enroute fueling required. Communicate with pilot to properly load aircraft for intended mission. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Contractor, Tanker Base Manager RAMP manager and Parking Tender
Flight Operations/ Base Operations | Dispatches late or early in the operational day | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Adhere to policies governing times airtankers can fly (i.e. startup and cutoff times). Provide aerial supervision when appropriate. Terminate flights where it is deemed the airtanker will arrive and there is insufficient light for safe operation. Adhere to policy for sunset and sunrise limitation on single engine aircraft. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Pilots, UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Flight Operations/ Base Operations | Increasing number of aircraft incidents | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Request a service visit from RASM, Regional Pilots and Mechanic Inspectors or request a STAT Team. File Safecoms when appropriate and monitor trends to determine need for assistance. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | UAM, FAO, Dispatch
Flight Operations/ Base Operations | Lack of pilot proficiency | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | The PIC will be authorized a 20 minute revenue flight and drop for pilot proficiency and to check airtanker systems if there has been no flight the prior 14 days. Flight authorized on the 15th day. Allow Pilots to maintain proficiency by following standards set in contract. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | UAM, FAO, Aircraft Managers
Flight Operations | Inbound aircraft with problems | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Unlikely | High | Follow Base Emergency Plan. Notify the fire department (911), the Airport Manager, and Airport Crash Rescue (if any). Meet the Fire Chief at the gate. Brief on type aircraft, specific problem, known hazards, fuel on board, and number of personnel in the aircraft, exit areas on the aircraft, and PIC’s plan and/or suggestions. Verify the fire department’s plans for staging, chase, and attack. Stay with Fire Chief to facilitate communication between the aircraft and rescue operations. Follow emergency plan for aircraft with mechanical or other problems. | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Rare | Moderate | Yes | Pilots, UAM, FAO, Tanker Base Manager or Assistant Tanker Base Manager
Flight Operations/ Base Operations | Complacency | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Aircraft accidents have a high fatality rate and are always serious and costly. Personnel working around and in aircraft must be highly trained and maintain a vigilant attitude. Periodic inspections of personnel, equipment, and operations will be performed. Maintain situation awareness and be prepared constantly | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | All base personnel.

## Instructions
The Risk Assessment Worksheet (RAW) will identify the hazards associated with a project, incident or work activity assessing initial risk, mitigations and post mitigation risk (residual risk).
Block 1 | Name of project, incident or work activty
Block 2 | Location of project, incident or work activity
Block 3 | Specific Objective
Block 4 | Name and title of person preparing the Risk Assesment Worksheet
Block 5 | Date that the preparer filled out the Risk Assesment Worksheet
Block 6 | If block 16 is Moderate, Serious or Critical, Use the Risk Decision Authority matrix to determine the authorization required to sign in block 6. The intent is to brief the Risk Decision Authority on the Control Measures used to reduce risks. Note: if the person preparing the form signs this block, the risk in block 17 must be Minor or Negliable.
Asses Hazards: See instructions for blocks 7-11
Block 7 | Task: task to be assessed (Driving, tree falling, stream assessment, mop up)
Block 8 | Hazards: Identify hazards (low visibility, overhead hazard, swift current, stump holes)
Block 9 | Hazard Probability: Probability a hazard will be encountered during task. Select from drop down box.
Block 10 | Severity/Consequence: Consequences should an event occur. Select from drop down box.
Block 11 | Risk Assessment Code (RAC): When blocks 09 and 10 are populated a Risk Assesment Code (RAC) will be automatically assigned.
Identify Risk Mitigation Measures: Identify mitigation and abatement measures in block 12
Block 12 | List all mitigation or abatement measures: What mitigation or abatement strategies will eliminate or minimize residual risk (ex. engineering, administrative, PPE, Avoidance, education, etc.)
Residual Risk: See instructions for blocks 13-17.
Block 13 | Severity/Consequence: Severity/consequence following mitigation or abatement actions. Select from drop down box.
Block 14 | Hazard Probabilty: Probability following mitigation or abatement actions. Select from drop down box.
Block 15 | Risk Assessment Code (RAC): When blocks 13 and 14 are populated a RAC in block 15 will be automatically assigned. Fill out the risk questionaire pop up and this will give you block 16.
Block 16 | Neccessary: Is the risk necessary following mitigation or abatement actions. Yes/No This will be auto-populated based on the answers provided on the risk questionaire. If the answer is No, either develop additional or alternate mitigations, modifications, or do not accept the risk.
Block 17 | Person or operational area assigned the abatement actions. This can be left blank.
Severity/Consequences
Catastrophic | Impact to objective (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment).
Critical | Impact to objective (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment).
Moderate | Impact to objective (Hospitalized minor injury, reversable illness; minor damage to equipment, property or the environment).
Negligible | Impact to objective (First aid or minor medical treatment; little or no property or environmental damage).
Probability
Almost Certain | Continuously experienced.
Likely | Will occur frequently.
Possible | Will occur several times.
Unlikely | Remotely possible but not probable.
Rare | Improbable; but has occurred in the past.
Definitions
Probability | The likelihood or the chance of an event occurring.
Severity | The magnitude of impacts or consequences stemming from an event.
Consequence | The outcome or effect of an event or incident, usually evaluated with respect to objectives.
Severity /Consequence | Both terms are used interchangeably, both refer to the impact that a hazard could have on the objective.
Hazard | Any real or potential condition that can cause damage, loss, or harm to people, infrastructure, equipment, natural resources, property or objective.
Risk | Risk is “the effect of uncertainty on objectives” typically expressed as an estimate of the probability and severity/consequence of uncertain future events

## RA Charts
Risk Assessment Matrix |  | Probability Likelihood of Mishap if Hazard is Present |  |  |  |  | Risk Decision Authority
|  | Almost Certain | Likely | Possible | Unlikely | Rare
|  | (Continuously experienced) | (Will occur frequently) | (Will occur several times) | (Remotely possible but not probable) | (Improbable; but has occurred in the past) | Risk Assessment Code | Project or Work Activity
Severity/ Consequences Consequence if Mishap Occurs | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Extremely High | Extremely High | Extremely High | High | Moderate | Extremely High | USFS Line Officer
| Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Extremely High | Extremely High | High | Moderate | Moderate | High | USFS Line Officer
| Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | High | High | Moderate | Low | Low | Moderate | Supervisor or Lead
| Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Moderate | Moderate | Low | Low | Low | Low | Individual
Severity/Consequences: Both terms are used interchangeably, both refer to the impact that a hazard could have on the objective. Should something go wrong, the results are likely to occur in one of these areas - Injury or Death, equipment damage, project/fire operations degradation, adverse publicity, environmental damage, property damage, etc.
Catastrophic |  | Impact to objective (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment).
Critical |  | Impact to objective (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment).
Moderate |  | Impact to objective (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment).
Negligible |  | Impact to objective (First aid or minor medical treatment; little or no property or environmental damage).
Probability: The likelihood or the chance of an event occurring.
Almost Certain |  | Continuously experienced.
Likely |  | Will occur frequently.
Possible |  | Will occur several times.
Unlikely |  | Remotely possible but not probable.
Rare |  | Improbable; but has occurred in the past.
Note on D5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on E5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on F5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on G5: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on H5: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on D6: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on E6: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on F6: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on G6: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on H6: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on D7: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on E7: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on F7: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on G7: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on H7: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on D8: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on E8: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on F8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on G8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on H8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment