## RA Worksheet
Risk Assessment Worksheet |  |  |  | 1. Project/Incident/Work Activity |  |  | 2. Location
|  |  |  | Batch Plant and Mix Transfer System Operations |  |  | Fishlake and Dixie National Forests
3. Specific Objective |  |  |  | 4. Name and Title of Preparer |  |  | 5. Date
To mix alumagel safely for use for precribed fire and fire suppression. |  |  |  | Clint Coates Forest Aviation Officer |  |  | 2023-01-18
6. Risk Decision Authority: (Authority Signature Block) If block 15 is Moderate, High or Extremely High a higher level of authority needs to sign in this block.
Signature/Date:
Assess Hazards |  |  |  |  | Identify Risk Mitigation Measures | Residual Risk
7. Task | 8. Hazard | 9. Severity/ Consequence | 10. Hazard Probability | 11. RAC | 12. List all mitigation or abatement measures | 13. Severity/ Consequences | 14. Hazard Probability | 15. RAC | 16. Necessary (Yes/No) | 17. Hazard Control Assigned to:
Driving , Batch Plant Trailer Towing Haz-Mat | Accident/Incident involving Haz-Mat | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Conduct pre-trip inspection, Only CDL drivers with hazmat & tanks endorsements may tow the batch plant trailer. Utilize aerial Ignition Guide: Regulatory Issues/Transportation Requirements and Inspection Checklist. Must have agency trailer endorsement for USFS. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Supervisors and individual assigned to tow batch plant
CDL Driving | Driving beyond service hour regulations | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Observe the fire program requirements on driving time and work/rest ratio. Agency records will provide proper evidence of driver’s hours of service. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Rare | Moderate | Yes | Incident Commander or Burn Boss Individual assigned to tow batch plant
Batch Plant/Mixing Operations | Improper use of equipment | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Read manufactures manual, and checklist. Wear proper PPE (static free clothing , hard hat, ear/eye protection, gloves, and boots). Ensure supervision by HTMM qualified operator. Become familiar with pump operation and valves prior to mixing fuel. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Helitorch Manager, Heltorch Mix Master and Mixing Crew
Batch Plant/Mixing Operations | Exposure to fuel vapors/chemical vapors and agents while mixing | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Take required aerial ignition training, comply with aerial ignition guide standards and wear required PPE, follow aerial ignition guide chapter 4, Fuel Preparation and MSDS Appendix C and Appendix F-Bonding Procedures. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Helitorch Manager, Heltorch Mix Master and Mixing Crew
Batch Plant/Mixing Operations | Risk of static electricity causing ignition of vapors | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Unlikely | High | Utilize approved aerial ignition equipment with static bonding throughout system, wear appropriate PPE fibers, no cell phones or radios within 50’ of mixing area. | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Rare | Moderate | Yes | Helitorch Manager, Heltorch Mix Master and Mixing Crew
Batch Plant/Mixing Operations | Slips, trips and falls from trailer | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Work methodically, keep surfaces dry and clean. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Helitorch Manager, Heltorch Mix Master and Mixing Crew
Batch Plant/Mixing Operations | Equipment malfunction or failure | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Complete daily helitorch mixing system checklist. Correct all identified issues. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Helitorch Manager, Heltorch Mix Master and Mixing Crew
Helicopter/Helibase Operations | Personnel not qualified or familiar with equipment. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | High | Ensure personnel are fully qualified and current with refresher training and certification in assigned position. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Moderate | Yes | Incident Commander or Burn Boss Individual assigned to tow batch plant Helitorch Manager

## Instructions
The Risk Assessment Worksheet (RAW) will identify the hazards associated with a project, incident or work activity assessing initial risk, mitigations and post mitigation risk (residual risk).
Block 1 | Name of project, incident or work activty
Block 2 | Location of project, incident or work activity
Block 3 | Specific Objective
Block 4 | Name and title of person preparing the Risk Assesment Worksheet
Block 5 | Date that the preparer filled out the Risk Assesment Worksheet
Block 6 | If block 16 is Moderate, Serious or Critical, Use the Risk Decision Authority matrix to determine the authorization required to sign in block 6. The intent is to brief the Risk Decision Authority on the Control Measures used to reduce risks. Note: if the person preparing the form signs this block, the risk in block 17 must be Minor or Negliable.
Asses Hazards: See instructions for blocks 7-11
Block 7 | Task: task to be assessed (Driving, tree falling, stream assessment, mop up)
Block 8 | Hazards: Identify hazards (low visibility, overhead hazard, swift current, stump holes)
Block 9 | Hazard Probability: Probability a hazard will be encountered during task. Select from drop down box.
Block 10 | Severity/Consequence: Consequences should an event occur. Select from drop down box.
Block 11 | Risk Assessment Code (RAC): When blocks 09 and 10 are populated a Risk Assesment Code (RAC) will be automatically assigned.
Identify Risk Mitigation Measures: Identify mitigation and abatement measures in block 12
Block 12 | List all mitigation or abatement measures: What mitigation or abatement strategies will eliminate or minimize residual risk (ex. engineering, administrative, PPE, Avoidance, education, etc.)
Residual Risk: See instructions for blocks 13-17.
Block 13 | Severity/Consequence: Severity/consequence following mitigation or abatement actions. Select from drop down box.
Block 14 | Hazard Probabilty: Probability following mitigation or abatement actions. Select from drop down box.
Block 15 | Risk Assessment Code (RAC): When blocks 13 and 14 are populated a RAC in block 15 will be automatically assigned. Fill out the risk questionaire pop up and this will give you block 16.
Block 16 | Neccessary: Is the risk necessary following mitigation or abatement actions. Yes/No This will be auto-populated based on the answers provided on the risk questionaire. If the answer is No, either develop additional or alternate mitigations, modifications, or do not accept the risk.
Block 17 | Person or operational area assigned the abatement actions. This can be left blank.
Severity/Consequences
Catastrophic | Impact to objective (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment).
Critical | Impact to objective (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment).
Moderate | Impact to objective (Hospitalized minor injury, reversable illness; minor damage to equipment, property or the environment).
Negligible | Impact to objective (First aid or minor medical treatment; little or no property or environmental damage).
Probability
Almost Certain | Continuously experienced.
Likely | Will occur frequently.
Possible | Will occur several times.
Unlikely | Remotely possible but not probable.
Rare | Improbable; but has occurred in the past.
Definitions
Probability | The likelihood or the chance of an event occurring.
Severity | The magnitude of impacts or consequences stemming from an event.
Consequence | The outcome or effect of an event or incident, usually evaluated with respect to objectives.
Severity /Consequence | Both terms are used interchangeably, both refer to the impact that a hazard could have on the objective.
Hazard | Any real or potential condition that can cause damage, loss, or harm to people, infrastructure, equipment, natural resources, property or objective.
Risk | Risk is “the effect of uncertainty on objectives” typically expressed as an estimate of the probability and severity/consequence of uncertain future events

## RA Charts
Risk Assessment Matrix |  | Probability Likelihood of Mishap if Hazard is Present |  |  |  |  | Risk Decision Authority
|  | Almost Certain | Likely | Possible | Unlikely | Rare
|  | (Continuously experienced) | (Will occur frequently) | (Will occur several times) | (Remotely possible but not probable) | (Improbable; but has occurred in the past) | Risk Assessment Code | Project or Work Activity
Severity/ Consequences Consequence if Mishap Occurs | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Extremely High | Extremely High | Extremely High | High | Moderate | Extremely High | USFS Line Officer
| Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Extremely High | Extremely High | High | Moderate | Moderate | High | USFS Line Officer
| Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | High | High | Moderate | Low | Low | Moderate | Supervisor or Lead
| Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Moderate | Moderate | Low | Low | Low | Low | Individual
Severity/Consequences: Both terms are used interchangeably, both refer to the impact that a hazard could have on the objective. Should something go wrong, the results are likely to occur in one of these areas - Injury or Death, equipment damage, project/fire operations degradation, adverse publicity, environmental damage, property damage, etc.
Catastrophic |  | Impact to objective (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment).
Critical |  | Impact to objective (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment).
Moderate |  | Impact to objective (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment).
Negligible |  | Impact to objective (First aid or minor medical treatment; little or no property or environmental damage).
Probability: The likelihood or the chance of an event occurring.
Almost Certain |  | Continuously experienced.
Likely |  | Will occur frequently.
Possible |  | Will occur several times.
Unlikely |  | Remotely possible but not probable.
Rare |  | Improbable; but has occurred in the past.
Note on D5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on E5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on F5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on G5: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on H5: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on D6: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on E6: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on F6: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on G6: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on H6: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on D7: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on E7: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on F7: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on G7: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on H7: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on D8: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on E8: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on F8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on G8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on H8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment