## RA Worksheet
Risk Assessment Worksheet |  |  |  | 1. Project/Incident/Work Activity |  |  | 2. Location
|  |  |  | Helicopter Seeding |  |  | Fishlake and Dixie National Forests
3. Specific Objective |  |  |  | 4. Name and Title of Preparer |  |  | 5. Date
To provide a safe and efficient working environment for employees working with helicopters during seeding operations |  |  |  | Clint Coates Forest Aviation Officer |  |  | 2023-01-18
6. Risk Decision Authority: (Authority Signature Block) If block 15 is Moderate, High or Extremely High a higher level of authority needs to sign in this block.
Signature/Date:
Assess Hazards |  |  |  |  | Identify Risk Mitigation Measures | Residual Risk
7. Task | 8. Hazard | 9. Severity/ Consequence | 10. Hazard Probability | 11. RAC | 12. List all mitigation or abatement measures | 13. Severity/ Consequences | 14. Hazard Probability | 15. RAC | 16. Necessary (Yes/No) | 17. Hazard Control Assigned to:
Seed Loading/ Helibase Operations | Injury from equipment and aircraft | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Wear proper PPE ( hard hat, ear protection, gloves, and boots). Other protection may be required on some jobs; eye protection and respiratory protection., Training, Tailgate Safety | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Project Manager Aircraft Manager
Seed Loading/ Helibase Operations | Movement of seeder/machine during service or maintenance | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Ensure the machine cannot be started or operated when in transport or servicing, Training, Tailgate Safety Briefing | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Project Manager Aircraft Manager
Seed Loading/ Helibase Operations | Slips and falls | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Ensure safe footing and hand holds. Keep oil/fuel spills clean. Wet boots or wet equipment increase hazard of slipping, Training, Tailgate Safety Briefing | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Project Manager Aircraft Manager
Seed Loading/ Helibase Operations/ Flight Operations | Unknown Responsibilities | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Prior to each project, operator will review appropriate portions of MASP. The project briefing will cover responsibilities and emergency procedures, Morning Safety briefing/evening debriefing | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Every person on project
Flight Operations | Pilot Qualifications | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Helicopter and Pilot shall be certified. Pilot and aircraft will be carded annually for seeding operations. Pilot will be knowledgeable and trained in seeding operations. Use of proper PPE by all. Pre- and Post Op briefings will be performed. Contract Requirements, OJ training from Contractor. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Aircraft Manager
Flight Operations | Aircraft Avoidance | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | See and avoid. Check MTR routes in advance. Practice risk management; confirm that Dispatch has made contact with schedulers to de-conflict. Fly established airport patterns, initiate and stay in radio contact. Morning Safety briefing/evening debriefing | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Contract Pilot
Flight Operations Environmental | Weather | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Use weather advisory. Maintain VFR minimums, cancel mission if necessary. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Contract pilot/Helicopter Manager/ Dispatch
Flight Operations Environmental | High/Hot/Heavy Flight Conditions | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Performance planning complete/insure accurate Load & Balance calculations. Do not place the aircraft in performance related situations. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Contract pilot/Helicopter Manager
Flight Operations | Low level obstacles | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Provide pilot with aerial hazard map, Complete a high level recon, no unnecessary low level flight. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Contract Pilot
Seed Loading/ Helibase Operations/ Flight Operations | Noise, Rotor wash | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Likely | High | Wear ear and eye protection. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Every person on project
Flight Operations | Pilot not familiar with area | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Supply hazard maps. Complete high-level recon prior to low-level work, project area identified | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Contract Pilot
Flight Operations | Unplanned aircraft events | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | All personnel equipped with required PPE and trained in crash procedures. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Rare | Moderate | Yes | Contractor pilot/Helicopter Manager
Seed Loading/ Helibase Operations/ Flight Operations | Hazardous materials | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Qualified personnel will handle, review MSDS, inform pilot. Use proper PPE. Driver of Fuel Service Vehicles will have current Hazmat endorsement and comply w/all federal/state/local laws. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Project Manager Aircraft Manager Contract Pilot
Seed Loading/ Helibase Operations/ Flight Operations | Communications | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Flight following established, checked and followed, communication plan posted. Maintain communications at all times, establish backup alternate frequencies. Take handheld radio along. Call in prior to landing. If radio contact is lost return to best suitable landing area and check-in. All hand held electronic devices such as radios, pagers, cell phones, etc. shall be turned off within 50’ of any fueling operations. Carry extra batteries, have back up radio | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Unlikely | Moderate | Yes | Project Manager Aircraft Manager Contract Pilot
Seed Loading/ Helibase Operations/ Flight Operations | Rotor Hazard | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Unlikely | High | Pilot performs aircraft safety brief, approach/depart safely or after shutdown and rotor stop. | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Rare | Moderate | Yes | Every person on project
Seed Loading/ Helibase Operations/ Flight Operations | Seeding bucket/ Equipment failure | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Visual inspection for cracks, loose bolts/nuts, hoses, etc. Check fluid levels to avoid failures due to inadequate levels of fuel, oil, coolant, etc. Inspect machine prior to use. Inspections by qualified person repair, correct or report as necessary. Tangled wires on seed bucket | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Project Manager Aircraft Manager Contract Pilot
Helicopter/Helibase Operations | Personnel not qualified or familiar with equipment. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Ensure personnel are fully qualified and current with refresher training and certification in assigned position. | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Unlikely | Low | Yes | Project Manager Aircraft Manager

## Instructions
The Risk Assessment Worksheet (RAW) will identify the hazards associated with a project, incident or work activity assessing initial risk, mitigations and post mitigation risk (residual risk).
Block 1 | Name of project, incident or work activty
Block 2 | Location of project, incident or work activity
Block 3 | Specific Objective
Block 4 | Name and title of person preparing the Risk Assesment Worksheet
Block 5 | Date that the preparer filled out the Risk Assesment Worksheet
Block 6 | If block 16 is Moderate, Serious or Critical, Use the Risk Decision Authority matrix to determine the authorization required to sign in block 6. The intent is to brief the Risk Decision Authority on the Control Measures used to reduce risks. Note: if the person preparing the form signs this block, the risk in block 17 must be Minor or Negliable.
Asses Hazards: See instructions for blocks 7-11
Block 7 | Task: task to be assessed (Driving, tree falling, stream assessment, mop up)
Block 8 | Hazards: Identify hazards (low visibility, overhead hazard, swift current, stump holes)
Block 9 | Hazard Probability: Probability a hazard will be encountered during task. Select from drop down box.
Block 10 | Severity/Consequence: Consequences should an event occur. Select from drop down box.
Block 11 | Risk Assessment Code (RAC): When blocks 09 and 10 are populated a Risk Assesment Code (RAC) will be automatically assigned.
Identify Risk Mitigation Measures: Identify mitigation and abatement measures in block 12
Block 12 | List all mitigation or abatement measures: What mitigation or abatement strategies will eliminate or minimize residual risk (ex. engineering, administrative, PPE, Avoidance, education, etc.)
Residual Risk: See instructions for blocks 13-17.
Block 13 | Severity/Consequence: Severity/consequence following mitigation or abatement actions. Select from drop down box.
Block 14 | Hazard Probabilty: Probability following mitigation or abatement actions. Select from drop down box.
Block 15 | Risk Assessment Code (RAC): When blocks 13 and 14 are populated a RAC in block 15 will be automatically assigned. Fill out the risk questionaire pop up and this will give you block 16.
Block 16 | Neccessary: Is the risk necessary following mitigation or abatement actions. Yes/No This will be auto-populated based on the answers provided on the risk questionaire. If the answer is No, either develop additional or alternate mitigations, modifications, or do not accept the risk.
Block 17 | Person or operational area assigned the abatement actions. This can be left blank.
Severity/Consequences
Catastrophic | Impact to objective (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment).
Critical | Impact to objective (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment).
Moderate | Impact to objective (Hospitalized minor injury, reversable illness; minor damage to equipment, property or the environment).
Negligible | Impact to objective (First aid or minor medical treatment; little or no property or environmental damage).
Probability
Almost Certain | Continuously experienced.
Likely | Will occur frequently.
Possible | Will occur several times.
Unlikely | Remotely possible but not probable.
Rare | Improbable; but has occurred in the past.
Definitions
Probability | The likelihood or the chance of an event occurring.
Severity | The magnitude of impacts or consequences stemming from an event.
Consequence | The outcome or effect of an event or incident, usually evaluated with respect to objectives.
Severity /Consequence | Both terms are used interchangeably, both refer to the impact that a hazard could have on the objective.
Hazard | Any real or potential condition that can cause damage, loss, or harm to people, infrastructure, equipment, natural resources, property or objective.
Risk | Risk is “the effect of uncertainty on objectives” typically expressed as an estimate of the probability and severity/consequence of uncertain future events

## RA Charts
Risk Assessment Matrix |  | Probability Likelihood of Mishap if Hazard is Present |  |  |  |  | Risk Decision Authority
|  | Almost Certain | Likely | Possible | Unlikely | Rare
|  | (Continuously experienced) | (Will occur frequently) | (Will occur several times) | (Remotely possible but not probable) | (Improbable; but has occurred in the past) | Risk Assessment Code | Project or Work Activity
Severity/ Consequences Consequence if Mishap Occurs | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Extremely High | Extremely High | Extremely High | High | Moderate | Extremely High | USFS Line Officer
| Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Extremely High | Extremely High | High | Moderate | Moderate | High | USFS Line Officer
| Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | High | High | Moderate | Low | Low | Moderate | Supervisor or Lead
| Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Moderate | Moderate | Low | Low | Low | Low | Individual
Severity/Consequences: Both terms are used interchangeably, both refer to the impact that a hazard could have on the objective. Should something go wrong, the results are likely to occur in one of these areas - Injury or Death, equipment damage, project/fire operations degradation, adverse publicity, environmental damage, property damage, etc.
Catastrophic |  | Impact to objective (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment).
Critical |  | Impact to objective (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment).
Moderate |  | Impact to objective (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment).
Negligible |  | Impact to objective (First aid or minor medical treatment; little or no property or environmental damage).
Probability: The likelihood or the chance of an event occurring.
Almost Certain |  | Continuously experienced.
Likely |  | Will occur frequently.
Possible |  | Will occur several times.
Unlikely |  | Remotely possible but not probable.
Rare |  | Improbable; but has occurred in the past.
Note on D5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on E5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on F5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on G5: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on H5: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on D6: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on E6: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on F6: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on G6: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on H6: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on D7: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on E7: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on F7: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on G7: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on H7: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on D8: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on E8: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on F8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on G8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on H8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment