## RA Worksheet
Risk Assessment Worksheet |  |  |  | 1. Project/Incident/Work Activity |  |  | 2. Location
|  |  |  | Sign Construction, Installation and Maintenance |  |  | Central Utah
3. Specific Objective |  |  |  | 4. Name and Title of Preparer |  |  | 5. Date
Sign Work Safety |  |  |  | Jill Ivie - Forest Fire Prevention |  |  | 2024-01-31
6. Risk Decision Authority: (Authority Signature Block) If block 15 is Moderate, High or Extremely High a higher level of authority needs to sign in this block.
Signature/Date:
Assess Hazards |  |  |  |  | Identify Risk Mitigation Measures | Residual Risk
7. Task | 8. Hazard | 9. Severity/ Consequence | 10. Hazard Probability | 11. RAC | 12. List all mitigation or abatement measures | 13. Severity/ Consequences | 14. Hazard Probability | 15. RAC | 16. Necessary (Yes/No) | 17. Hazard Control Assigned to:
Proper PPE | Not wearing it | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | You MUST wear appropriate Personal Protective Equipment (PPE) such as a hard hat, ear protection, gloves, boots, eye protection, and breathing protection. Other protection may be required on some jobs | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Impairment of hearing | Exposure to loud noise | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Ear protection must be worn by crewmembers; plug type ear protection or full ear coverage devices (muff type). | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Vehicles passing by | Injury | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Install safety signs to alert traffic of your presence. Some work areas may require wearing reflective safety vests or other highly visible clothing. When in doubt wear visible clothing. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Sight safety | Injury | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | You MUST wear wraparound goggles or safety glass type protection or a hard hat mounted face shield for full protection of the face. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Slipping, tripping, and falling | Injury | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Wear heavy-duty, leather boots with good tread. Make sure laces are tied/secure at all times. Watch your footing wherever you are. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Back safety | Injury | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Warm up muscles prior to lifting heavier objects. Lift only what feels comfortable. Ask for help when lifting heavy objects. Use mechanical devices to help lift and move materials. Keep your back straight when lifting and lift with your legs. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Personal first aid needs | Not being prepared | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Let coworkers know of your medical condition and manner to treat if medical attention is needed. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Breathing | Difficulties | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Make paper filter type dust masks or aspirators available. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Head and hands | Injury | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Always wear an approved hardhat to protect your head and leather gloves to protect your hands. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Lost or missing | Potential injury from prolonged exposure | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Inform supervisor & fire dispatch of your general location for work activities planned for each day. If your location changes significally, notify your supervisor/fire dispatch. Call office/fire dispatch or another crew member if you expect to arrive back to the office more than an hour of normal quit time. Upon arrival notify your supervisor & fire dispatch by phone/radio. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Field project leader
Cuts, scrapes, insect bites/stings | Injury, discomfort, allergic reactions | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Ensure first aid kits are available & adequately supplied with up to date items. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Use of power tools | Electrocution, severe burns, cuts, and abrasions | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Only qualified personnel shall operate power equipment. Immediate supervisor shall authorize permission, prior to operation, of power tools. Keep electrical cords, plugs, and switches in good condition. Keep tools clean, in good working order, and ensure safety guards are suitable. Return tools to appropriate storage areas when done. Wear appropriate PPE such as earplugs, gloves, safety glasses, hardhat, face shield, mask to protect from fumes, and/or other PPE that may be necessary for the safety of the operator and other personnel on site. Use power tools as recommended by the manufacturer. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Improper use of vehicles or accident resulting form lack of vehicle maintenance | Death of serious injury | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Perform daily vehicle check to assure fuel and oil is adequeate, a walk around check to assure tires are properly inflated, no oil leaks are apparent, and general condition of the vehicle is suitable for operations. Clean vehicle routinely. Assure first aid kit is available and stocked for use. Charged fire extinguisher, tire chains, jack/lug wrench, shovel, ax, and daily tools should be in good working order and readily accessible. Use vehicles for official use only. Drive defensively; permit authorized drivers to operate vehicles; use chock blocks when vehicles are parked. Park in areas sufficiently wide enough to permit use of road by passing vehicles; if narrow, place cones to delineate your space. Avoid backing vehicles whenever possible. When backing have an observer available to assist giving backing directions and observe potencial hazards. Secure contents of vehicle to assure materials do not blow out, bounce out, fall out, or otherwise exit the vehicle to cause damage or injury to following vehicles. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Improper use of hand tools | Injury including cuts, head woulds from falling tools or materials, falling from ladders or stools | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Use hand tools such as saws, wrenches, hammers, ladders, shovels, posthole diggers, tamping rods, etc. in a manner intended and recommended by the manufacturer. Stabilize ladder or stools prior to climbing. Keep tools in serviceable condition, repair or replace tools that are not serviceable. Keep the work area sufficiently organized to prevent tripping or falling over tools. When working overhead, secure materials and/or tools so that they may not drop and injure other personnel in the work area. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Exposure to weather conditions | Sunburn, dehydration, hypothermia, and heat exhaustion/dehydration | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Wear approprriate clothing for weather conditions such as long sleeve shirt, long pants, and/or a neck bandana. Drink plenty of water, stay warm and dry, layer clothing, and avoid sunburn. Know your physical ability. Rest periodically. Let your coworkers know if you feel symptoms developing. The best defense for heat related illness is prevention…drink lots of fluids (nonalcoholic), regardless of your activity level. Don’t wait until you’re thirsty to drink. If your doctor generally limits the amount of fluid you drink or has you on water pills, ask him how much you should drink while the weather is hot. Don’t drink liquids that contain caffeine, alcohol, or large amounts of sugar–these actually cause you to lose more body fluid. Also, avoid very cold drinks, because they can cause stomach cramps. Wear lightweight, light-colored, loose-fitting clothing. NEVER leave anyone in a closed, parked vehicle. While vigorously working, drink two to four glasses of cool (nonalcoholic) fluids each hour. A sports beverage can replace the salt and minerals you lose in sweat. If you are on a low-salt diet, talk with your doctor before drinking a sports beverage. Try to rest often in shady areas. Protect yourself from the sun by wearing an approved hardhat (also keeps you cooler) and sunglasses (safety glasses while working) and by putting on sunscreen of SPF 15 or higher. Take frequent short rest breaks to “cool down”. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Exposure to chemically treated materials | Injury | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Avoid frequent or prolonged inhalation of sawdust from treated wood. Sawing, sanding and machining of treated wood should be performed outdoors while wearing personal protective equipment (PPE). PPE consists of a dust mask, goggles, gloves, earplugs, leather boots, a long sleeve shirt and long pants. Because preservative or sawdust may accumulate on clothes, launder before reuse. Wash work clothes separately from other household clothing. Wear gloves when handling treated wood. After working with treated wood and before eating, drinking, toileting and use of tobacco products, wash exposed areas thoroughly. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Skin or eye irritation | Affixation, illness, inhalation, burns or contaminates | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Ask for and read Materials Safety Data Sheets (MSDS) and Product Warning Labels prior to application of paints, solvents, and other products you may encounter. Wear appropriate PPE as identified in the MSDS. Incidental storage of flammables/combustibles must be in an NFPA approved storage cabinet and labeled "Flammable - keep Fire Away". Never store flammable/combustible liquids in office areas except those required for maintenance and operation of building and equipment. Such storage must be in closed metal containers in a storage cabinet or in safety containers. Do NOT use aerosol paint. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
On/off loading signs and supplies | Personal injury or equipment damage | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Use ground guide during on/off loading. Ensure trailer is level. Lift with legs and not your back. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Securing loads | Shifting loads | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Ensure all equipment and materials are properly tied down and/or sucured. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Improper use of or poor judgment when working on/near heavy equipment | Death or injury to self and/or others | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | EM-7130-2 Driver-Operator Guide has specific operating instructions and safety rules for each piece of heavy equipment. Operators and workers assigned to projects shall review and follow the instructions. Review road maintenance risk assessment prior to commencing work. Stay well away from equipment while idling or working, only approch equipment when specifically directed by the operator- avoid pinch points. Use extreme caution when near equipment. The equipment operator is in charge of the project and will provide guidance and direction to other workers. Work activity is subordinate to the equipment operator’s direction. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Use of ATV’s / UTV’s | Head and eye injuries | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Wear an approved helmet meeting the Standards of ANSI, SOT, or SMF. Always fasten the chin strap on the helmet. Watch for low hanging limbs. Never follow other vehicles or ATV’s/UTV’s closely to prevent rocks or ther debris from being kicked up. Wear a helmet face shield or goggles (sunglasses may be used if not provided) for adequate protection. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Failure to properly hitch trailers to tow vehicles, verify the roadworthiness of the trailer and tow vehicle, and verify all equipment is properly stowed. | May cause serious injury or death to yourself and others. | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Tow vehicle must have proper towing capacity for the trailer being towed. Check the tow vehicles operating manual for rated capacity. Do NOT tow the trailer unless all the important checks listed below are satisfactorily completed: 1) Hitch is secure to tow vehicle and safety pin/latch is secured. 2) Frame must be level or the tongue slighlty lower than the rear of the equipment while towing to ensure proper weight distribution. The hitch may have to be adjusted when towing with vehicles of varying toe hitch height. 3) Safety chains installed correctly. 4) Chains routed under the trailer tongue in an “X” pattern between tow vehicle and trailer. 5) Slack in chain should be adjusted to permit turning but not dragging on the ground. 6) Connect trailer wiring to the tow vehicle and ensure that all trailer lighting is operating properly. 7) Ensure the safety breakaway switch (if provided) is functioning properly and attached securely to the tow vehicle. Allow enough slack to ensure the vehicle turns will not activate the safety breakaway switch. NOTE: follow manufactures procedure to ensure tow vehicles brake control box is properly adjusted. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Loss of control with All-Terrain Vehicles (ATV’s) and Utility Task Vehicles (UTV’s). | Injury and/or property damage | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Travel at safe speeds for the nature of terrain. Avoid steep grades and steep side slopes. Shift weight forward while traveling up grades, shift weight back while traveling down grades. Never ride past the limit of your visibility. Keep your weight uphill and all times. Shift into lower gear and speed up BEFORE climbing a hill. If the ATV/UTV begins to tip, turn the front wheels downhill if the terrain allows. If the terrain does not permit, dismount on the uphill side immediatley. When carrying equipment, equalize the load to maintain balance, stability, and center of gravity. Never exceed the recommended gross vehicle weight. Secure loads with tie downs, bungee cords and/or straps. Load and unload ATV’s/UTV’s in a manner consistent with the manufactures recommentdations of the loading/unloading devise being used. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Dealing with angry or violent individuals | Physical injury | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Unlikely | Low | If a person approaches you and looks angry or threatening use your radio to alert the operator or swamper. Even if you are in an area where you cannot transmit, you can give the impression that you are in radio contact. Try to be intentional in your actions, you may feel intimidated, but act in control. Keep cool. If the person you are speaking to is angry, listen - do not react. Refer those who disagree with BLM/FS policy to your supervisor or the district ranger/field office manager. Never get into a private vehicle. If you are stranded, radio for help, stay in your rig until help arrives. If you meet individuals on isolated roads, stay in your vehicle; let them approach you. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Operating ATV’s/UTV’s | Cuts, abrasions, and foot injury | Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | Possible | Moderate | Long sleeve shirt, long pants, and leather boots are a minimum to protect arms, legs, and feet. Off-road riding gear, such as a jersey and shoulder pads/chest protector and off-road pants with knee and shin protection provides better protection. Keep your feet firmly on the ATV footrest or within UTV cab. Personal Protective Equipment (PPE): fire extiguisher, first aid kit, personal communications device, motorcyle helmet (full or ¾ face), mouth protection is recommended when using ¾ face helmets, the helmet shall meet requirements of the Department of Transportaion (DOT), ANSI (Z90.1) or Snell Memorial Foundations (SMF) standards, leather gloves, long pants and long-sleeve shirt or jacket, appropriate footware, and eye protection (such as goggles/glasses, or face shield). | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project
Not thinking clearly and making mistakes | May lead to accident/injury | Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Possible | High | Listen for 'The Alarm' - We often receive a subtle, internal warning about an unsafe act before an incident occurs. Tune in to the warning, often manifested as an uneasy feeling or idea that something is wrong. This feeling is diminished when we repeat an unsafe act many times without consequences. It is also diminished when we are in such a hurry or are so preoccupied that the matter distracts us from feeling different when faced with an unsafe situation. Listen for 'The Alarm' and heed the warning the first time! Slow down and remain focused on the task. Step Back, Think, Organize, Proceed - Step back and consider all aspects of the job. Think about what you are about to do. Organize the job and co-workers to ensure quality and quantity of task accomplishment. Proceed in a determined effort to accomplish given tasks in a safe manner. | Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Possible | Low | Yes | Every person on project

## Instructions
The Risk Assessment Worksheet (RAW) will identify the hazards associated with a project, incident or work activity assessing initial risk, mitigations and post mitigation risk (residual risk).
Block 1 | Name of project, incident or work activty
Block 2 | Location of project, incident or work activity
Block 3 | Specific Objective
Block 4 | Name and title of person preparing the Risk Assesment Worksheet
Block 5 | Date that the preparer filled out the Risk Assesment Worksheet
Block 6 | If block 16 is Moderate, Serious or Critical, Use the Risk Decision Authority matrix to determine the authorization required to sign in block 6. The intent is to brief the Risk Decision Authority on the Control Measures used to reduce risks. Note: if the person preparing the form signs this block, the risk in block 17 must be Minor or Negliable.
Asses Hazards: See instructions for blocks 7-11
Block 7 | Task: task to be assessed (Driving, tree falling, stream assessment, mop up)
Block 8 | Hazards: Identify hazards (low visibility, overhead hazard, swift current, stump holes)
Block 9 | Hazard Probability: Probability a hazard will be encountered during task. Select from drop down box.
Block 10 | Severity/Consequence: Consequences should an event occur. Select from drop down box.
Block 11 | Risk Assessment Code (RAC): When blocks 09 and 10 are populated a Risk Assesment Code (RAC) will be automatically assigned.
Identify Risk Mitigation Measures: Identify mitigation and abatement measures in block 12
Block 12 | List all mitigation or abatement measures: What mitigation or abatement strategies will eliminate or minimize residual risk (ex. engineering, administrative, PPE, Avoidance, education, etc.)
Residual Risk: See instructions for blocks 13-17.
Block 13 | Severity/Consequence: Severity/consequence following mitigation or abatement actions. Select from drop down box.
Block 14 | Hazard Probabilty: Probability following mitigation or abatement actions. Select from drop down box.
Block 15 | Risk Assessment Code (RAC): When blocks 13 and 14 are populated a RAC in block 15 will be automatically assigned. Fill out the risk questionaire pop up and this will give you block 16.
Block 16 | Neccessary: Is the risk necessary following mitigation or abatement actions. Yes/No This will be auto-populated based on the answers provided on the risk questionaire. If the answer is No, either develop additional or alternate mitigations, modifications, or do not accept the risk.
Block 17 | Person or operational area assigned the abatement actions. This can be left blank.
Severity/Consequences
Catastrophic | Impact to objective (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment).
Critical | Impact to objective (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment).
Moderate | Impact to objective (Hospitalized minor injury, reversable illness; minor damage to equipment, property or the environment).
Negligible | Impact to objective (First aid or minor medical treatment; little or no property or environmental damage).
Probability
Almost Certain | Continuously experienced.
Likely | Will occur frequently.
Possible | Will occur several times.
Unlikely | Remotely possible but not probable.
Rare | Improbable; but has occurred in the past.
Definitions
Probability | The likelihood or the chance of an event occurring.
Severity | The magnitude of impacts or consequences stemming from an event.
Consequence | The outcome or effect of an event or incident, usually evaluated with respect to objectives.
Severity /Consequence | Both terms are used interchangeably, both refer to the impact that a hazard could have on the objective.
Hazard | Any real or potential condition that can cause damage, loss, or harm to people, infrastructure, equipment, natural resources, property or objective.
Risk | Risk is “the effect of uncertainty on objectives” typically expressed as an estimate of the probability and severity/consequence of uncertain future events

## RA Charts
Risk Assessment Matrix |  | Probability Likelihood of Mishap if Hazard is Present |  |  |  |  | Risk Decision Authority
|  | Almost Certain | Likely | Possible | Unlikely | Rare
|  | (Continuously experienced) | (Will occur frequently) | (Will occur several times) | (Remotely possible but not probable) | (Improbable; but has occurred in the past) | Risk Assessment Code | Project or Work Activity
Severity/ Consequences Consequence if Mishap Occurs | Catastrophic (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment) | Extremely High | Extremely High | Extremely High | High | Moderate | Extremely High | USFS Line Officer
| Critical (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment) | Extremely High | Extremely High | High | Moderate | Moderate | High | USFS Line Officer
| Moderate (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment) | High | High | Moderate | Low | Low | Moderate | Supervisor or Lead
| Negligible (First aid or minor medical treatment; little or no property or environmental damage) | Moderate | Moderate | Low | Low | Low | Low | Individual
Severity/Consequences: Both terms are used interchangeably, both refer to the impact that a hazard could have on the objective. Should something go wrong, the results are likely to occur in one of these areas - Injury or Death, equipment damage, project/fire operations degradation, adverse publicity, environmental damage, property damage, etc.
Catastrophic |  | Impact to objective (Imminent and immediate danger of death or permanent disability; major property or facility damage; loss of critical system or equipment).
Critical |  | Impact to objective (Permanent partial disability, temporary total disability; moderate environmental damage; extensive damage to equipment).
Moderate |  | Impact to objective (Hospitalized minor injury, reversible illness; minor damage to equipment, property or the environment).
Negligible |  | Impact to objective (First aid or minor medical treatment; little or no property or environmental damage).
Probability: The likelihood or the chance of an event occurring.
Almost Certain |  | Continuously experienced.
Likely |  | Will occur frequently.
Possible |  | Will occur several times.
Unlikely |  | Remotely possible but not probable.
Rare |  | Improbable; but has occurred in the past.
Note on D5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on E5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on F5: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on G5: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on H5: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on D6: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on E6: • Complete or near complete failure to meet objective • Major property or facility damage • Death or permanent total disability • Severe environmental damage • Loss of major or critical system or equipment
Note on F6: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on G6: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on H6: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on D7: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on E7: • Significantly degraded capability for meeting the objective or accomplishing the project/incident/work activity • Injury that results in permanent partial disability, or temporary total disability lasting more than three months • Serious environmental damage
Note on F7: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on G7: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on H7: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on D8: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on E8: • Degraded capability for meeting objective or accomplishment of the project/fire operation • Lost days due to injury or illness not exceeding three months • Moderate damage to property or the environment
Note on F8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on G8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment
Note on H8: • No adverse impact to meeting objective or accomplishment of the project/fire operation • Little or no medical treatment required • Little or no damage to equipment, systems, property or environment