## Slide 1: Lessons from the Thirtymile Fire
<number>
USDA Forest Service
Missoula Technology & Development Center
0251-2C02-MTDC
Table of Contents
User Note: If you open links within this program, use the following options to return to your previous PowerPoint slide:
Try first to use the browser BACK button or the keyboard BACKSPACE key
If that option is not available, click the ‘X’ in the top right corner of your web browser window to close it.
Notes: <number>

## Slide 2: Overview
<number>
USDA Forest Service
Missoula Technology & Development Center
This training is based on the events of the Thirtymile Fire. You will get more out of this training if you read the Thirtymile Fire Investigation Report before the training.
This program can be used as self-paced training for individuals or as instructor-facilitated group training.
Notes: <number>

## Slide 3: Objectives
<number>
USDA Forest Service
Missoula Technology & Development Center
1. Provide a chronological overview of the key events and fire behavior on the Thirtymile Fire that led to the entrapment of 14 firefighters and 2 civilians and to the deaths of 4 of the firefighters.
Notes: <number>

## Slide 4: Objectives
<number>
USDA Forest Service
Missoula Technology & Development Center
2. The trainees will create a list of pivotal events and contributing factors on the Thirtymile Fire:
  Before entrapment
  After entrapment but before deployment
  During deployment
Notes: <number>

## Slide 5: Objectives
<number>
USDA Forest Service
Missoula Technology & Development Center
3. Emphasize the importance of avoiding entrapment.
Define the actions firefighters should take if they become entrapped.
Notes: <number>

## Slide 6: Objectives
<number>
USDA Forest Service
Missoula Technology & Development Center
4. Emphasize the concepts demonstrated in current fire shelter training aids.
Address the critical importance of leadership during entrapment and deployment.
Notes: <number>

## Slide 7: Introduction
<number>
USDA Forest Service
Missoula Technology & Development Center
Many direct and indirect influences led to the entrapment and fatalities on the Thirtymile Fire.
This program focuses only on the key events before and during the entrapment and fire shelter deployment.
Notes: <number>

## Slide 8: BEFORE ENTRAPMENT
<number>
USDA Forest Service
Missoula Technology & Development Center
Notes: <number>

## Slide 9: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
On July 10, 2001, 14 firefighters and 2 civilians were entrapped by the Thirtymile Fire in Washington State.
Four firefighters were asphyxiated during fire shelter deployment.
Notes: <number>

## Slide 10
<number>
USDA Forest Service
Missoula Technology & Development Center
Maps of northern Washington and the Thirtymile Fire location.
Notes: <number>

## Slide 11
<number>
USDA Forest Service
Missoula Technology & Development Center
Map of Washington and the Thirtymile Fire location.
Notes: <number>

## Slide 12
<number>
USDA Forest Service
Missoula Technology & Development Center
Map of northern Washington and the Thirtymile Fire location.
Notes: <number>

## Slide 13
<number>
USDA Forest Service
Missoula Technology & Development Center
Map of the Thirtymile Fire location.
Notes: <number>

## Slide 14: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Conditions when the fire started:
  The Okanogan-Wenatchee National Forest was experiencing prolonged drought
  Fuel moisture levels were at or approaching historic lows
  1,000-hour fuel moisture was 10%
  Live fuel moisture was less than 100%
  The energy release component (ERC) was near the historic high for early July
Notes: <number>

## Slide 15: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
The fire started next to the Chewuch River in the bottom of a narrow, V-shaped canyon.
Fuels in the riparian area where the fire started were mostly spruce, alder, and aspen.
A mix of fir, lodgepole pine, and ponderosa pine was present in the drier surrounding area.
Notes: <number>

## Slide 16
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view of the Chewuch River near the origin of the Thirtymile Fire, looking upcanyon.
Notes: <number>

## Slide 17
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view of the Chewuch River with the fire's origin in the lower right of the photo.
Notes: <number>

## Slide 18: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 9
  2126: Fire was reported by Canadian Bird Dog aircraft, estimated at 5 acres.
  2300: Three-person hand crew arrived; initial assessment was that the fire had burned 3 to 8 acres in heavy timber. Flame lengths were 2 to 4 feet.
  2345: Engine 704 arrived.
  2359: Revised initial attack assessment by the Engine 704 supervisor: the fire had burned 20 to 25 acres. "It will grow, hit the slope, and get larger."
Notes: <number>

## Slide 19
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire growth map showing the fire's origin and spot fires.
Notes: <number>

## Slide 20: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  0000: Northwest Regular (NWR) crew 6 began to assemble at Leavenworth, WA.
  0000: Eleven members of the crew were from the Lake/Leavenworth Ranger District and 10 were from the Naches Ranger District; all were from the Okanogan-Wenatchee National Forest.
  0000: Crew management consisted of a crew boss and a crew boss trainee.
Notes: <number>

## Slide 21: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  0000: The majority of NWR crew 6 got just 1 or 2 hours of sleep before dispatch.
  0000: The Entiat interagency hotshot crew (IHC) was dispatched to the Thirtymile Fire. The Entiat crew had worked all day on another fire. Crewmembers had little sleep, if any, during the previous 30 hours.
Notes: <number>

## Slide 22: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  0100: The Entiat crew arrived at the Thirtymile Fire. After a briefing by the initial attack incident commander (IC), the Entiat superintendent took over as IC.
  0100: All resources other than the Entiat crew were released. The Entiat crew began to take suppression action.
  0400: NWR crew 6 began the 3-hour drive to Twisp, WA.
  0700: NWR crew 6 arrived at Twisp and was assigned to the Thirtymile Fire. They were led to the fire by the forest and district fire management officers (FMOs). They did not have a map of the area.
Notes: <number>

## Slide 23: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  0900: NWR crew 6 arrived at the Thirtymile Fire. The Entiat superintendent, NWR crew 6 management, and forest and district fire management officers (FMOs) discussed strategy.
  0900: District FMO requested that a barrier be placed on the road to keep the public from entering the area.
  0900+: NWR crew 6 crew boss took over as IC but retained his role as crew boss. The crew boss trainee conducted the crew briefing.
Notes: <number>

## Slide 24: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  1100: Entiat crew went to a campground downcanyon from the fire to rest. NWR crew 6 began to take suppression action.
  1200: NWR crew 6 was unable to keep pumps operating. Crew boss trainee decided to change strategy and tactics.
  1200: NWR crew 6 began constructing indirect handline to pinch the head of the fire. Some crewmembers knew this was a "watchout situation."
  1300: Two civilians drove up the Chewuch River road past the fire to the Thirtymile campground. The road had not been closed as requested.
Notes: <number>

## Slide 25
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire growth map showing the fire's origin and the fire area between 10 a.m. and 3:20 p.m.
Notes: <number>

## Slide 26: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  1300: NWR crew 6 crewmember was sent to wake the Entiat crew and return them to the fire.
  1311: Air attack arrived over the fire.
  1400: The Entiat crew returned to the fire.
  1400+: Because of threatening fire behavior, the IC removed the crewmember serving as a lookout on the east side of the river.
  1430: Crew boss trainee suggested that the Entiat crew take over the fire. The Entiat foreman declined, saying: "This is nothing we want to mess with either. We did not have any anchor, spots everywhere. There wasn't anything we could do."
Notes: <number>

## Slide 27: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  Conditions on the afternoon of July 10,
  from a representative weather station:
  Temperature was about 101 °F.
  Relative humidity was 4%.
Notes: <number>

## Slide 28: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  1500: NWR crew 6 disengaged and took a break on the west side of the river next to the road. It was generally conceded that suppression efforts had been ineffective and that the fire would continue to grow.
  1500: District assistant fire management officer (AFMO) met with IC and crew boss trainee. AFMO asked IC if he was still comfortable as IC. The IC said he was.
  1500: AFMO suggested that it would be "nice" to keep the fire east of the road.
Notes: <number>

## Slide 29: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  1517: Road closure sign was posted by Engine 704.
  1520: Fire began making uphill crowning runs on the east slope of the canyon.
  1530: Engines 701 and 704 arrived at the Thirtymile Fire. The foreman on engine 701 checked in with the incident commander and explained that the engines would proceed up the Chewuch River Canyon Road to patrol for spot fires. The engines drove past the crew on the road and started to work on spot fires about 1/4 mile up the canyon.
Notes: <number>

## Slide 30
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial photo showing the fire's origin and the spot where fire crossed the road.
Notes: <number>

## Slide 31: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  1603: First Butte lookout reported that the fire column was forming a thunderhead (plume-dominated column with an ice cap).
Notes: <number>

## Slide 32
<number>
USDA Forest Service
Missoula Technology & Development Center
The plume-dominated Thirtymile Fire smoke column.
Notes: <number>

## Slide 33: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  1603+: Shortly after arrival, Engine 701 called the IC and requested help to suppress a spot fire up the canyon from the main fire. Squad 1 of NWR crew 6 was assigned to support the engines.
  1603+: Within minutes after squad 1 arrived, Engine 701 drove down the canyon to work on other spot fires.
Notes: <number>

## Slide 34: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  1620: Squad 2 of NWR crew 6 was called to support Engine 701 on another spot fire.
  1634: Fire on the canyon floor began making sustained torching runs in tree crowns.
  1634: Fire was actively spotting and was adjacent to the east side of the road.
Notes: <number>

## Slide 35
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial photo showing fuels where fire eventually crossed the road.
Notes: <number>

## Slide 36: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  1634+: Squad 3 of NWR crew 6 was assigned to assist Engine 704.
  1634+: Within minutes of their arrival, squad 3 retreated down the canyon in their van.
  1634+: The Entiat crew superintendent advised the IC to get people out of the area.
Notes: <number>

## Slide 37
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire growth map showing the fire's origin, the entrapment area, and the fire area between 3:20 and 4:40 p.m.
Notes: <number>

## Slide 38: Before Entrapment
<number>
USDA Forest Service
Missoula Technology & Development Center
Chronology: July 10
  1634+: The IC and nine members of NWR crew 6 jumped in the other crew van and drove down the road. Four other crewmembers began running down the road on foot.
  1634+: All 14 crewmembers were cut off by fire on both sides of the road and could not retreat down the canyon.
Notes: <number>

## Slide 39
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire crossing the road, with Engine 704 and Entiat IHC vehicles in the foreground.
Notes: <number>

## Slide 40: BETWEEN ENTRAPMENT AND DEPLOYMENT
<number>
USDA Forest Service
Missoula Technology & Development Center
Notes: <number>

## Slide 41
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial photo taken by air attack around the time of the entrapment.
Notes: <number>

## Slide 42
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial photo taken by air attack around the time of the entrapment.
Notes: <number>

## Slide 43: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
The firefighters were entrapped; the road ended about 3 miles up the canyon.
They were unaware at this time that two civilians had also been entrapped.
Notes: <number>

## Slide 44: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Entrapment
  1634+: After the fire cut off the van's retreat, the IC picked up the four crewmembers who were on foot.
  1634+: All 14 crewmembers drove up the canyon in the van. The IC evaluated four possible sites as potential safety zones.
  1634+: With the assistance of air attack, the IC selected a site where he felt "they could safely watch the fire pass them by." The chosen site was about 1 mile up the canyon from the area where the fire crossed the road.
Notes: <number>

## Slide 45
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial photo looking down the Chewuch River canyon toward the southwest.
Notes: <number>

## Slide 46: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
The deployment area was characterized by rock scree above the road.
The Chewuch River and a sandbar were just below the road.
Notes: <number>

## Slide 47: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Forest vegetation was relatively sparse in this area.
On the east side of the river just down the canyon from the site, a rock slump created a wide fuel break.
Notes: <number>

## Slide 48
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view of the deployment area.
Notes: <number>

## Slide 49: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Entrapment
  The firefighters arrived at the selected site about 30 minutes before the fire front.
  Some firefighters were concerned that the site was not an adequate safety zone and that a deployment might be necessary.
  Although they had time to prepare for a deployment, there was very little preparation.
  The entrapped firefighters experienced different levels of anxiety about their situation. They "hung out" and "watched the show" as the fire approached.
Notes: <number>

## Slide 50
<number>
USDA Forest Service
Missoula Technology & Development Center
Photo taken by an entrapped crewmember watching the crown fire approach, looking downcanyon.
Notes: <number>

## Slide 51: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Entrapment
  The squad 2 squad boss scouted the scree slope as a potential deployment site, but eventually recommended to the IC that the road would be a better deployment site.
  Six Naches Ranger District employees clustered together on rocks about 20 feet above the road, watching the approaching fire. The IC and eight crewmembers remained on the road.
Notes: <number>

## Slide 52
<number>
USDA Forest Service
Missoula Technology & Development Center
A pack on the road. Rocks at the upper center of this photo are where the Naches District firefighters were located.
Notes: <number>

## Slide 53
<number>
USDA Forest Service
Missoula Technology & Development Center
The upper deployment site, looking downcanyon.
Notes: <number>

## Slide 54: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Entrapment
  At 1700, air attack estimated the fire was over 500 acres.
  Two well developed and counter-rotating convection columns had formed, one on the hillside east of the river and one in the canyon bottom.
Notes: <number>

## Slide 55
<number>
USDA Forest Service
Missoula Technology & Development Center
Plume-dominated columns from the Thirtymile Fire.
Notes: <number>

## Slide 56
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire growth map showing the fire's origin, the fire area by 5 p.m., and the deployment area.
Notes: <number>

## Slide 57: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Entrapment
  Shortly after 1700, two civilians arrived at the site.
  No briefing was given, and no personal protective equipment (PPE) was made available to the civilians.
  Before deployment, the civilians put on long pants, hats, and long-sleeved shirts.
  The civilians' vehicle was eventually destroyed by the fire.
Notes: <number>

## Slide 58
<number>
USDA Forest Service
Missoula Technology & Development Center
The civilians' vehicle, parked at the lower deployment site, was destroyed by the fire.
Notes: <number>

## Slide 59: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Entrapment
  Although crewmembers had been watching the fire's steady approach, at 1724 the behavior of the fire became dramatically more intense at the site.
  The crew was not in a heightened state of readiness and was overwhelmed by the abrupt change.
Notes: <number>

## Slide 60
<number>
USDA Forest Service
Missoula Technology & Development Center
Photo taken by an entrapped firefighter just before deployment.
Notes: <number>

## Slide 61: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Entrapment
  It is not possible to determine what caused the surge of fire behavior that led to the fatalities on the Thirtymile Fire.
  Although no major weather event affected the fire, the prevailing winds and canyon direction combined to give an upcanyon boost to the crown fire.
Notes: <number>

## Slide 62
<number>
USDA Forest Service
Missoula Technology & Development Center
Photo taken by an entrapped firefighter just before deployment.
Notes: <number>

## Slide 63: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Entrapment
  The extremely low fuel moisture levels in the valley's dense timber stands, combined with hot, dry weather, provided the conditions for a plume-dominated timber crown fire.
Notes: <number>

## Slide 64
<number>
USDA Forest Service
Missoula Technology & Development Center
The plume-dominated column of the Thirtymile Fire.
Notes: <number>

## Slide 65: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Entrapment
  The shape and steepness of the canyon slope influenced the fire's behavior. The fire made multiple runs on the densely forested eastern canyon wall.
Notes: <number>

## Slide 66
<number>
USDA Forest Service
Missoula Technology & Development Center
The east canyon wall after the crown fire.
Notes: <number>

## Slide 67
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire growth map showing the fire's origin, the fire area by 5:30 p.m., and the deployment area.
Notes: <number>

## Slide 68: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Entrapment
  The timber stands were dense and continuous in the valley floor down the canyon from the entrapped firefighters.
Notes: <number>

## Slide 69
<number>
USDA Forest Service
Missoula Technology & Development Center
Fuels on the valley floor. The fire's origin is at the middle right of the photo.
Notes: <number>

## Slide 70: Between Entrapment and Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Entrapment
  From the point where the fire crossed the road, the crown fire in the canyon bottom had almost a mile of continuous, dense timber in which to make an upcanyon run.
Notes: <number>

## Slide 71
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view of Thirtymile Fire location, looking down the Chewuch River Canyon toward the southwest.
Notes: <number>

## Slide 72: DEPLOYMENT
<number>
USDA Forest Service
Missoula Technology & Development Center
Notes: <number>

## Slide 73
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view of the deployment sites.
Notes: <number>

## Slide 74
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view of the deployment sites, looking downcanyon.
Notes: <number>

## Slide 75: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  1724+: Embers rained down as the flaming front and plume of hot gases reached the crewmembers and civilians. The fire's approach was described as "coming very fast, roaring" and sounding like a "freight train."
  1724+: Within moments, the firefighters and civilians were faced with a life-threatening situation. There was no longer a question about whether this area was a safety zone or a deployment site.
Notes: <number>

## Slide 76
<number>
USDA Forest Service
Missoula Technology & Development Center
Photo taken by an entrapped firefighter of embers and flames just before deployment.
Notes: <number>

## Slide 77: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  When fire engulfed the site, the IC told the crewmembers on the road to "get your shelters out and use (them) against the ash."
  Very shortly afterward he told the crewmembers on the road to deploy.
Notes: <number>

## Slide 78: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  Just before deployment, one crewmember left her Naches crewmates on the rocks and joined the firefighters on the road.
  When the fire arrived, she allowed the two civilians inside her shelter. Although it was a very tight fit, the three people crouched under the shelter and survived the fire's impact.
Notes: <number>

## Slide 79: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  The arrival of the fire front severely affected the six firefighters on the slope.
  The squad 2 squad boss was coming down through the rocks and was about 40 or 50 feet away from the road when the flames came at him from across the canyon.
  He turned and ran back up the slope before he deployed his fire shelter.
Notes: <number>

## Slide 80
<number>
USDA Forest Service
Missoula Technology & Development Center
Photo taken by an entrapped firefighter as flames approached.
Notes: <number>

## Slide 81: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  The five Naches District crewmembers on the hill ran upslope right behind the squad 2 squad boss.
  The squad 2 squad boss yelled "Deploy, deploy, deploy" as he was getting into his fire shelter.
Notes: <number>

## Slide 82
<number>
USDA Forest Service
Missoula Technology & Development Center
Scree slope at the upper deployment site.
Notes: <number>

## Slide 83: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  The six crewmembers deployed about 100 feet upslope from the road in a tight cluster.
  They were on rocks 6 inches to 3 feet in diameter.
  Heavy accumulations of fuels were in the rocks.
  Two of the firefighters who deployed at the upper site survived.
  Initially, the two survivors from the upper site heard voices from the other firefighters deployed near them. After a short period, the voices ceased.
Notes: <number>

## Slide 84
<number>
USDA Forest Service
Missoula Technology & Development Center
The upper deployment site.
Notes: <number>

## Slide 85: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  At the upper deployment site, the squad 2 squad boss saw his fire shelter begin to burn and fill with smoke. He became convinced he would not survive if he stayed where he was.
  After a few minutes, the squad boss abandoned his shelter, ran through the rock scree down to the road, and jumped in the river.
  The squad boss was wearing full personal protective equipment (PPE), including a shroud. He received only minor burns during the deployment and run to the river.
Notes: <number>

## Slide 86
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view looking upcanyon, with upper and lower deployment sites marked.
Notes: <number>

## Slide 87: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  The other surviving crewmember from the upper site deployed his shelter next to the squad 2 squad boss.
  He was not wearing gloves.
  His hands were severely burned from holding his shelter down and attempting to extinguish flames within his shelter.
Notes: <number>

## Slide 88
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view looking downcanyon, with deployment sites in the center of the photo.
Notes: <number>

## Slide 89: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  After a few minutes, the burned crewmember from the upper site also abandoned his shelter and moved toward the road.
  He considered jumping in the river, but was concerned about the potential for shock because of his burned condition, and took refuge in the crew van.
Notes: <number>

## Slide 90
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view of the deployment sites, with the van's location marked.
Notes: <number>

## Slide 91
<number>
USDA Forest Service
Missoula Technology & Development Center
Photo of the van just before deployment.
Notes: <number>

## Slide 92: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  The only damage to the van was melted plastic license plate brackets.
Notes: <number>

## Slide 93
<number>
USDA Forest Service
Missoula Technology & Development Center
The van suffered almost no damage during the fire.
Notes: <number>

## Slide 94: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  After the firefighters and civilians on the road had been under their fire shelters for a short while, the IC told them to join the squad 2 squad boss in the river.
  After about 15 minutes in the river, they all moved to the sandbar. Some of the firefighters became very cold from immersion in the river.
Notes: <number>

## Slide 95
<number>
USDA Forest Service
Missoula Technology & Development Center
A shelter and pack on the sandbar, with the road in the background.
Notes: <number>

## Slide 96
<number>
USDA Forest Service
Missoula Technology & Development Center
A shelter on the river bank downriver from the sandbar.
Notes: <number>

## Slide 97: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  At the upper deployment site, the four Naches Ranger District crewmembers were overcome by the fire.
Notes: <number>

## Slide 98: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  Although the four firefighters were able to deploy their shelters, they were unable to protect their airways. They were asphyxiated after inhaling hot gases.
  Based on the accounts of the two survivors from the upper deployment site, the victims probably succumbed to the effects of the initial wave of heat.
Notes: <number>

## Slide 99: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  Needles and limbs on trees adjacent to the deployment sites were deformed by a strong, hot, wind coming from the downcanyon crown fire.
  The "heat set" on needles and limbs indicates the general winds at the deployment area were upcanyon and upslope.
Notes: <number>

## Slide 100
<number>
USDA Forest Service
Missoula Technology & Development Center
This tree beside the lower deployment site shows the effects of "heat set."
Notes: <number>

## Slide 101: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  Air temperatures in the upper deployment area were estimated to have been between 1,200 and 1,600 °F.
  These temperatures far exceed the protective capabilities of fire shelters.
Notes: <number>

## Slide 102
<number>
USDA Forest Service
Missoula Technology & Development Center
Charred rocks at the upper deployment site.
Notes: <number>

## Slide 103: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  The upper deployment site was less than ideal. Heavy concentrations of woody fuels were scattered among the rocks on the scree slope.
  The rocks were from 6 inches to several feet in diameter.
  It would have been very difficult, if not impossible, to obtain a good seal around the shelters at this site. Gas and flames could pass through holes between the rocks underneath the shelters.
Notes: <number>

## Slide 104
<number>
USDA Forest Service
Missoula Technology & Development Center
Rocks at the upper deployment site.
Notes: <number>

## Slide 105: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  Firefighters at the upper deployment site did not discuss where to deploy.
  They did move a short distance uphill, instinctively moving away as the heat hit them.
  The firefighters deployed at the upper site because extreme conditions made it impossible to go any farther.
Notes: <number>

## Slide 106: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  Many of the firefighters had difficulty deploying their shelters in the winds generated by the fire.
Notes: <number>

## Slide 107
<number>
USDA Forest Service
Missoula Technology & Development Center
Trees near the deployment sites were deformed (heat set) by hot winds and gases.
Notes: <number>

## Slide 108: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  Some firefighters deployed with their heads facing the flames, or deployed face up.
  Some firefighters kept their packs on as they deployed their shelters.
  Other firefighters dropped their packs right next to their shelters. Burning packs damaged several fire shelters.
Notes: <number>

## Slide 109
<number>
USDA Forest Service
Missoula Technology & Development Center
Packs on the road at the lower deployment site.
Notes: <number>

## Slide 110: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  Within seconds after the arrival of the fire front, firebrands started spot fires at both deployment sites.
  Shelters at both sites were damaged because firefighters deployed their shelters over fuel concentrations or too close to adjacent fuels.
Notes: <number>

## Slide 111
<number>
USDA Forest Service
Missoula Technology & Development Center
This shelter at the lower deployment site was damaged by contact with burning fuels.
Notes: <number>

## Slide 112: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  Firefighters who deployed in the road away from fuels were exposed to temperatures lower than 500 °F.
  Their shelters showed little or no heat damage.
Notes: <number>

## Slide 113
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire shelters and packs along the roadside at the lower deployment site.
Notes: <number>

## Slide 114
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire shelters alongside the road. Some firefighters deployed their shelters toward the center of the road.
Notes: <number>

## Slide 115: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  After the fire front had passed, the Entiat superintendent organized the hotshot crew to rescue the entrapped firefighters and civilians.
  The NWR 6 crew boss trainee and four members of the Entiat crew made several attempts to reach the entrapped firefighters. The intense heat and fallen trees made it impossible to drive up the road. About 30 minutes passed before they were able to get to the deployment area.
Notes: <number>

## Slide 116: Deployment
<number>
USDA Forest Service
Missoula Technology & Development Center
Key Events: Deployment
  After arriving at the deployment area, the Entiat superintendent attempted to reach the upper deployment site, but could not get close because of the intense heat.
  It became obvious that the four firefighters in the upper deployment site were not alive.
Notes: <number>

## Slide 117: Questions?
<number>
USDA Forest Service
Missoula Technology & Development Center
Notes: <number>

## Slide 118: Group Exercise
<number>
USDA Forest Service
Missoula Technology & Development Center
Notes: <number>

## Slide 119: Exercise Guidelines
<number>
USDA Forest Service
Missoula Technology & Development Center
Your instructor will facilitate an exercise based on the Thirtymile Fire.
  The challenge is to describe the pivotal events and contributing factors on the Thirtymile Fire.
  If you criticize a decision, an action, or the failure to take an action, suggest what should have occurred.
Notes: <number>

## Slide 120: Exercise Guidelines
<number>
USDA Forest Service
Missoula Technology & Development Center
This exercise will focus on what happened, not on who was responsible.
We will compare your "size-up" with the conclusions presented in this training program.
Notes: <number>

## Slide 121: Exercise Topic
<number>
USDA Forest Service
Missoula Technology & Development Center
Before Entrapment
Notes: <number>

## Slide 122: Exercise Topic
<number>
USDA Forest Service
Missoula Technology & Development Center
Between Entrapment and Deployment
Notes: <number>

## Slide 123: Exercise Topic
<number>
USDA Forest Service
Missoula Technology & Development Center
Deployment
Notes: <number>

## Slide 124: LESSONS LEARNED
<number>
USDA Forest Service
Missoula Technology & Development Center
Notes: <number>

## Slide 125: Intentional Omissions
<number>
USDA Forest Service
Missoula Technology & Development Center
  This training does not cover all significant factors discussed in the Thirtymile Fire Investigation Report.
  Competition for attention with the larger Libby South fire, management decisions, use of aviation resources, communication problems, leadership issues, fatigue, lack of situation awareness, lack of crew cohesiveness, and other important factors were not covered during the chronology of fire events.
  This training focuses on the events immediately before and during the entrapment, when decisions by supervisors could have prevented the entrapment or saved lives.
Notes: <number>

## Slide 126: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  The arrival of the fire engines and the decision to have NWR crew 6 reengage and attack spot fires up the canyon set in motion a chain of events with tragic consequences.
  Almost immediately after the crew reengaged, the fire crossed the road behind them. The entrapped firefighters were only minutes away from the most catastrophic event of their lives.
  A lack of situation awareness by fire supervisors led to the entrapment.
  The entrapped firefighters made a series of critical errors before and during the deployment.
Notes: <number>

## Slide 127
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial photo showing the fire's origin and the spot where fire crossed the road.
Notes: <number>

## Slide 128: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  The potential effects of the crown fire's power were underestimated by the entrapped firefighters.
  Although they were uncertain about what would happen when the fire front arrived, the speed and severity of the event surprised them.
  Because the entrapped firefighters underestimated the severity of the situation, they failed to use the available time to improve their chances of surviving.
Notes: <number>

## Slide 129
<number>
USDA Forest Service
Missoula Technology & Development Center
Photo taken by one of the entrapped firefighters as flames approached.
Notes: <number>

## Slide 130: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
After entrapment, the firefighters had enough time to:
  Select a single deployment site
  Brief firefighters and civilians on what to expect
  Check and prepare PPE
  Reduce adjacent fuels
  Put line gear away
  Get shelters out
  Take a head count
  Make other preparations
None of this was done.
Notes: <number>

## Slide 131: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  The behavior of the Thirtymile Fire throughout the shelter deployment event was probably not unprecedented for a crown fire.
  What was unusual was that people were in the path of a timber crown fire run during extreme burning conditions.
Notes: <number>

## Slide 132
<number>
USDA Forest Service
Missoula Technology & Development Center
Timber crown fires release enormous amounts of energy.
Notes: <number>

## Slide 133: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  Timber crown fires release enormous amounts of energy and do not always grow in a predictable fashion.
  Plume-dominated fires can create strong indrafts and downdrafts. The fire behavior that results can be severe and erratic. Indrafts and downdrafts may have contributed to the extreme, erratic fire behavior on the Thirtymile Fire.
Notes: <number>

## Slide 134
<number>
USDA Forest Service
Missoula Technology & Development Center
Timber crown fires release enormous amounts of energy.
Notes: <number>

## Slide 135: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  The winds generated by crown fires are strong enough to topple trees.
  Winds generated by the Thirtymile Fire uprooted hundreds of trees upcanyon from the deployment area.
Notes: <number>

## Slide 136
<number>
USDA Forest Service
Missoula Technology & Development Center
Winds generated by the Thirtymile Fire uprooted hundreds of trees.
Notes: <number>

## Slide 137: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  Crown fires can produce life-threatening conditions far from the main body of the fire.
  The sudden wave of heat, gas, and embers that threatened the entrapped firefighters was generated from a source several hundred feet away.
Notes: <number>

## Slide 138
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view of the entrapment area. The arrow shows the general direction of the wind.
Notes: <number>

## Slide 139
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view of the entrapment area. The arrow shows the general direction of the wind.
Notes: <number>

## Slide 140: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  Firefighters should anticipate that terrain similar to the Chewuch River canyon can channel a fire's energy, making areas unsurvivable even though they might appear to be safe.
Notes: <number>

## Slide 141
<number>
USDA Forest Service
Missoula Technology & Development Center
Aerial view of the Chewuch River canyon.
Notes: <number>

## Slide 142: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  The size of the rocks at the upper deployment site made it nearly impossible to obtain a good seal around the fire shelters.
  Hot gases within the shelters would have diminished the firefighters' abilities to protect themselves.
Notes: <number>

## Slide 143
<number>
USDA Forest Service
Missoula Technology & Development Center
Rocks at the upper deployment site.
Notes: <number>

## Slide 144: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  Dry logs, limbs, and decomposing woody materials scattered throughout the upper site began burning early in the deployment and contributed to a high level of heat in that area.
Notes: <number>

## Slide 145
<number>
USDA Forest Service
Missoula Technology & Development Center
Woody debris at the upper deployment site.
Notes: <number>

## Slide 146
<number>
USDA Forest Service
Missoula Technology & Development Center
Burned logs at the upper deployment site.
Notes: <number>

## Slide 147: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  Although the upper and lower deployment sites were separated by only about 100 feet horizontally and 15 feet of elevation, conditions at the two sites were very different.
  The slightly higher position of the upper entrapment site may have been significant. The firefighters at that location were more vulnerable to the heat impact.
Notes: <number>

## Slide 148
<number>
USDA Forest Service
Missoula Technology & Development Center
The upper deployment site, looking back toward the road.
Notes: <number>

## Slide 149: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
The upper deployment site was not a good deployment site for several reasons:
  It was too close to the standing timber.
  Large rocks made it difficult to get a good seal around the fire shelters.
  Burnable fuels were scattered among the rocks.
  The slightly higher position on the slope made it more vulnerable to heat impact than the road or river sites.
Notes: <number>

## Slide 150
<number>
USDA Forest Service
Missoula Technology & Development Center
The upper deployment site.
Notes: <number>

## Slide 151: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  The deaths of the firefighters at the upper deployment site should not prevent firefighters from considering rockslides as safety zones or deployment sites.
  Rockslides can be a good place to take refuge under the right conditions.
  Firefighters will have to evaluate each situation to make those determinations.
Notes: <number>

## Slide 152: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  The two survivors from the upper site left their shelters after a few minutes because they felt they would not survive there. They were the only survivors from the upper site.
  Moving after deployment may have been their only chance for survival, but they were very fortunate to have survived.
  Getting out of your shelter during a deployment cannot be recommended. When you open your shelter you expose your airway to hot gases—a potentially fatal move.
Notes: <number>

## Slide 153: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  The decision to deploy on the road was a good one. There was insignificant damage to the van and everyone who deployed on the road survived.
  The firefighters on the road who deployed away from adjacent fuels and packs were exposed to temperatures lower than 500 °F. Afterward, their shelters were largely undamaged.
Notes: <number>

## Slide 154: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  Generally, it is best to stay as low on the slope as possible. Roads and flat areas can also be good places to deploy because they can keep you below the path of flames and convective heat.
  In all cases you must avoid chimneys, saddles, draws, and adjacent fuels [see Fire Shelter Deployment: Avoid the Flames brochure for more information].
Notes: <number>

## Slide 155
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire shelters alongside the road. Some firefighters deployed their shelters toward the center of the road.
Notes: <number>

## Slide 156: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  The Thirtymile Fire shelter deployment reinforces previous knowledge of fire shelter performance.
  If fire shelters are properly deployed in a survivable site away from fuels or packs, they can save your life.
Notes: <number>

## Slide 157: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  The sandbar or river might have been the best deployment site in the area.
  Most of the crew moved to the river after the initial deployment.
  The decision of some of the firefighters to get in the river was a good one in this case. The water was relatively shallow and slow. There was little chance of the firefighters being swept away or drowned.
Notes: <number>

## Slide 158
<number>
USDA Forest Service
Missoula Technology & Development Center
Sandbar, river, pack, and fire shelter.
Notes: <number>

## Slide 159: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  The water provided a large heat sink. It could absorb a lot of heat without becoming hot itself. The firefighters were able to breathe easier next to the cold water.
  Despite the intense heat around them, the firefighters who took refuge in the river became very cold after about 15 minutes in the water. They recovered quickly after they left the river.
Notes: <number>

## Slide 160
<number>
USDA Forest Service
Missoula Technology & Development Center
The deployment sites were close to the river.
Notes: <number>

## Slide 161: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  Firefighters should be aware of the dangerous effects of hypothermia, even on a hot day during a fire.
  If firefighters are forced to take refuge in water, they should monitor each other for signs of hypothermia.
Notes: <number>

## Slide 162: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  Some of the firefighters took their shelters to the river and used them to protect themselves from radiant heat and embers while they were in the water. This was a good decision.
Notes: <number>

## Slide 163
<number>
USDA Forest Service
Missoula Technology & Development Center
A fire shelter on the river bank.
Notes: <number>

## Slide 164: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  Water sources have been used as refuges on many wildfires. Firefighters should avoid swift-moving, deep, or very shallow water.
  If a shelter is deployed in moving water, the current may try to pull the shelter downstream. Don't allow yourself to become entangled in the shelter's straps.
Notes: <number>

## Slide 165
<number>
USDA Forest Service
Missoula Technology & Development Center
A fire shelter on the river bank.
Notes: <number>

## Slide 166: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
    She came down from the rocks to the road.
    She protected two civilians in her shelter.
  Her decision to protect the civilians was in keeping with firefighters' directive to protect lives.
  The civilians may not have survived on their own.
  One firefighter made two crucial decisions during the entrapment:
Notes: <number>

## Slide 167
<number>
USDA Forest Service
Missoula Technology & Development Center
The civilians' vehicle, parked at the lower deployment site, was destroyed by the fire.
Notes: <number>

## Slide 168: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
  Firefighters have an obligation to assist others who are threatened by a wildfire—especially persons who are non-firefighters.
  Civilians cannot be expected to know how to react in an entrapment.
Notes: <number>

## Slide 169: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Personal Protective Equipment
  At the upper deployment site, the two surviving firefighters deployed fire shelters beside each other and were exposed to similar conditions. They both abandoned their shelters after a few minutes and relocated to the road and river.
  One was severely burned on his hands and face, while the other received only minor burns.
Notes: <number>

## Slide 170: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Personal Protective Equipment
  The firefighter who received minor burns was wearing leather gloves and had a flame-resistant shroud covering his face during the deployment.
  The other firefighter left his gloves in a vehicle and was not wearing a shroud.
  This is a powerful testament to the effectiveness of these PPE items. While on a wildfire, all firefighters should have gloves within reach and a shroud readily available.
Notes: <number>

## Slide 171
<number>
USDA Forest Service
Missoula Technology & Development Center
Firefighter wearing a shroud.
Notes: <number>

## Slide 172: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Personal Protective Equipment
  Shrouds should only be used in escape and entrapment situations to protect firefighters from injury.
  They should not be used to protect firefighters from heat so they can work closer to the fire.
Notes: <number>

## Slide 173
<number>
USDA Forest Service
Missoula Technology & Development Center
Firefighter wearing a shroud.
Notes: <number>

## Slide 174: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Personal Protective Equipment
  If you temporarily remove your gloves, attach them to a carabiner on your belt, or secure them somewhere else on your person so you will be able to get them quickly.
Notes: <number>

## Slide 175
<number>
USDA Forest Service
Missoula Technology & Development Center
Gloves hung from a belt loop with a carabiner.
Notes: <number>

## Slide 176: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Entrapment Avoidance
  Entrapment avoidance should always be a priority for wildland firefighters. Firefighters should never take an assignment based on the assumption that a fire shelter may be needed as a contingency.
Notes: <number>

## Slide 177: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Entrapment Reaction
  Firefighters should test their entrapment reaction skills through drills.
  At the Thirtymile Fire valuable time was wasted between entrapment and deployment.
  If there is enough time after entrapment, use the time to plan for a deployment.
Notes: <number>

## Slide 178: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Entrapment Reaction
  Fire supervisors should be encouraged to run entrapment drills frequently and without warning.
  Entrapment drills should test firefighters' abilities to recognize and acknowledge entrapment.
  Drills that include more than one firefighter should require trainees to designate a person in charge. The person in charge, with the assistance of others, will select the best course of action.
Notes: <number>

## Slide 179: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Entrapment Reaction
  The PPE check during an entrapment drill should include:
    Flame-resistant pants
    Leather boots
    Flame-resistant shirt buttoned to top, sleeves down
    Leather gloves on
    Hardhat with shroud deployed
    Eye protection
    Fire shelter in hand
    Hand tool in hand
    Line gear off and away from deployment area
Notes: <number>

## Slide 180: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Entrapment Reaction
  Chain saws, gas, oil, fusees, packs, and other flammable items should be placed far enough from the deployment area to prevent them from harming the firefighters if the items should ignite.
Notes: <number>

## Slide 181: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire Shelter Deployment
  To ensure that firefighters retain the skills needed in an emergency, fire supervisors should have their employees perform fire shelter deployment drills at regular intervals during the fire season.
  An entrapment drill should always precede a fire shelter deployment drill.
  Firefighters should become used to combining the sets of skills required to successfully survive an entrapment and fire shelter deployment.
Notes: <number>

## Slide 182: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire Shelter Deployment
  Actual fire shelter deployments are extremely stressful to the participants.
  DO NOT expose firefighters to flames or other dangerous conditions.
  DO strive to provide realistic and stressful conditions during fire shelter deployment drills.
Notes: <number>

## Slide 183: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors
  An analysis of the Thirtymile Fire would not be complete without acknowledging important human factors:
    Lack of crew cohesion
    Fatigue
    Lack of situation awareness
    Lack of leadership
Notes: <number>

## Slide 184: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors—Crew Cohesion
  The NWR crew 6 included members from the Naches and Lake/Leavenworth Ranger Districts.
  Many of the crewmembers from one district did not know the members from the other district.
  Members from the two districts did not function as one cohesive crew with one leader.
Notes: <number>

## Slide 185: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors—Crew Cohesion
  Lack of cohesion within the NWR crew 6 became apparent after the entrapment.
  It is common for crews with little cohesion to fracture into familiar groupings when faced with a crisis.
  All of the firefighters who perished at the upper deployment site were from the Naches Ranger District.
Notes: <number>

## Slide 186: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors—Crew Cohesion
  Crew cohesion takes time to develop—as long as 6 to 8 weeks.
  Supervisors of newly formed crews should be aware of this problem, and should pay extra attention to communications and command and control during critical situations.
Notes: <number>

## Slide 187: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors—Fatigue
  Fatigue clouded the judgment and thinking of many of the firefighters. Fatigue made it hard for the firefighters to maintain awareness of what was happening around them, and to make good decisions.
  According to the Thirtymile Fire Investigation Report:
    "...the loss of even a single night's sleep (25.1 hours of wakefulness) impairs decision-making and vigilance levels comparable to a blood alcohol content of .10..." (p. 80).
Notes: <number>

## Slide 188: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors—Situation Awareness
  Key personnel lacked situation awareness during critical stages of the Thirtymile Fire.
  A lack, or temporary loss, of situation awareness is a factor in every entrapment.
  In dynamic situations, firefighters need to communicate nonstop to help maintain their situation awareness.
Notes: <number>

## Slide 189: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors—Leadership
  Survivors of the entrapment stated that instructions given by the IC were unclear, not heard, or interpreted by crewmembers in different ways.
  Once firefighters acknowledge that they are entrapped, they should immediately identify who will be in charge of the entrapped personnel.
Notes: <number>

## Slide 190: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors—Leadership
  Once the person in charge is confirmed, entrapped firefighters should obey that person's orders until the entrapment is over.
  Entrapments are stressful. Firefighters are often distracted by the fire and other activities that may be taking place.
  The person in charge during an entrapment may need to be more assertive than normal to ensure that firefighters receive and understand orders.
Notes: <number>

## Slide 191: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors—Leadership
  The person in charge during an entrapment should:
    Locate and count entrapped personnel
    Use available expertise, including air resources and lookouts, to help plan a course of action.
Notes: <number>

## Slide 192: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors—Leadership
  Once the entrapment plan is in place, all entrapped firefighters should stay together in the location that has been judged to be the safest.
  Regardless of the perceived threat, preparations for a deployment should be made at once.
Notes: <number>

## Slide 193: Risk Management
<number>
USDA Forest Service
Missoula Technology & Development Center
Notes: <number>

## Slide 194: Lessons Learned
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors—Risk Management
  Firefighters should always perform a risk assessment before beginning an assignment and when conditions change.
  They should not allow confusion or their focus on the mission to cause them to ignore the risk management process.
Notes: <number>

## Slide 195: DISCUSSION TOPIC
<number>
USDA Forest Service
Missoula Technology & Development Center
1. Fight fire aggressively but provide for safety first.
2. Initiate all action based on current and expected fire behavior.
3. Recognize current weather conditions and obtain forecasts.
4. Ensure instructions are given and understood.
5. Obtain current information on fire status.
6. Remain in communication with crewmembers, your supervisor, and adjoining forces.
7. Determine safety zones and escape routes.
8. Establish lookouts in potentially hazardous situations.
9. Retain control at all times.
10. Stay alert, keep calm, think clearly, and act decisively.
Consider each of the 10 Standard Fire Orders.
Was each order followed during the Thirtymile Fire?
Notes: <number>

## Slide 196: 10 Standard Fire Orders
<number>
USDA Forest Service
Missoula Technology & Development Center
The Thirtymile Fire Investigation Report concluded that "...all 10 Standard Fire Orders were violated or disregarded at some time during the course of the incident." (See Standard Fire Orders section, page 40)
Notes: <number>

## Slide 197: DISCUSSION TOPIC
<number>
USDA Forest Service
Missoula Technology & Development Center
1. Fire not scouted and sized up.
2. In country not seen in daylight.
3. Safety zones and escape routes not identified.
4. Unfamiliar with weather and local factors influencing fire behavior.
5. Uninformed on strategy, tactics, and hazards.
6. Instructions and assignments not clear
7. No communication link with crewmembers/supervisors.
8. Constructing line without safe anchor point.
9. Building fireline downhill with fire below.
10. Attempting frontal assault on fire.
11. Unburned fuel between you and the fire.
12. Cannot see main fire, not in contact with anyone who can.
13. On a hillside where rolling material can ignite fuel below.
14. Weather is getting hotter and drier.
15. Wind increases and/or changes direction.
16. Getting frequent spot fires across line.
17. Terrain and fuels make escape to safety zones difficult.
18. Taking a nap near the fireline.
How many of the 18 Watchout Situations were present?
Notes: <number>

## Slide 198: 18 Watchout Situations
<number>
USDA Forest Service
Missoula Technology & Development Center
The Thirtymile Fire Investigation Report concluded that "Ten of the eighteen Watch Out Situations were present or disregarded at some time during the course of the incident." (See Watch Out Situations section, page 42)
Notes: <number>

## Slide 199: DISCUSSION TOPIC
<number>
USDA Forest Service
Missoula Technology & Development Center
LCES is built on two guidelines:
1. Before safety is threatened, LCES should be established:
  Lookouts
  Communications
  Escape routes
  Safety zones
2. LCES must be continuously reevaluated as fire conditions change.
How well were these guidelines followed on the Thirtymile Fire?
Lookouts—Communications—Escape Routes—Safety Zones (LCES)
Notes: <number>

## Slide 200: LCES and Risk Management
<number>
USDA Forest Service
Missoula Technology & Development Center
The Thirtymile Fire Investigation Report concluded that the entire incident was characterized by ineffective risk management and inconsistent use of LCES principles (see page 82 of the Appendix on Human Factors).
Notes: <number>

## Slide 201: TRAINING AIDS & INFORMATION RESOURCES
<number>
USDA Forest Service
Missoula Technology & Development Center
In light of the fatalities at the Thirtymile Fire, current training aids for fire shelter training were reexamined to determine if alterations or additions were needed.
The information in current Fire Shelter training materials is correct and should be followed. Our understanding of the Thirtymile Fire does not indicate a need to revise current fire shelter training materials.
We did learn several critical lessons that will enhance fire shelter training.
Notes: <number>

## Slide 202: Training Aids & Information Resources
<number>
USDA Forest Service
Missoula Technology & Development Center
Fire Shelters
  The aids for fire shelter training include:
    Using Your Fire Shelter (video, 2001 NFES, #1568)
    New Generation Fire Shelter (MTDC-0351-2803)
    Avoid the Flames (brochure, 1999)
    This training program, Lessons from the Thirtymile Fire, (now part of the approved fire shelter training).
Notes: <number>

## Slide 203: Training Aids & Information Resources
<number>
USDA Forest Service
Missoula Technology & Development Center
Entrapment Avoidance
  The new Entrapment Avoidance training program provides firefighters with tools and communication techniques that are designed to prevent entrapments.
  The Entrapment Avoidance training program does not cover what to do after an entrapment has occurred.
Notes: <number>

## Slide 204: Training Aids & Information Resources
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors
  Training programs such as Human Factors on the Fireline and Fireline Leadership teach skills that can help firefighters cope with complex, dynamic situations.
Notes: <number>

## Slide 205: Training Aids & Information Resources
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors
  The papers from the Wildland Firefighters Human Factors Workshop of 1995 are available electronically in Findings From the Wildland Firefighters Human Factors Workshop (9551-2855-MTDC).
Notes: <number>

## Slide 206: Training Aids & Information Resources
<number>
USDA Forest Service
Missoula Technology & Development Center
Human Factors
  Dr. Jon Driessen of the Missoula Technology and Development Center (MTDC) has studied the relationship of crew cohesion to safety.
  His paper Crew Cohesion, Wildland Fire Transition, and Fatalities (0251-2809-MTDC) provides new insights into the challenges associated with crew cohesion.
Notes: <number>

## Slide 207: Training Aids & Information Resources
<number>
USDA Forest Service
Missoula Technology & Development Center
Incident Response Pocket Guide
  The 2002 Incident Response Pocket Guide contains several revisions that relate directly to entrapment avoidance and entrapments.
  The pocket guide is an excellent source of information for wildland firefighters.
Notes: <number>

## Slide 208: Key Messages
<number>
USDA Forest Service
Missoula Technology & Development Center
In a meeting of the Forest Service National Leadership Team held on March 20, 2002, the Chief provided the following key messages regarding deployment survival:
  The 10 Standard Fire Orders are firm rules of engagement. All decisions to engage, disengage, or re-engage in a suppression action must be made in terms of the 10 Standard Fire Orders.
  Following the fire orders is a personal responsibility and a shared obligation.
  If your escape route is compromised, do not delay preparations for deployment.
  Stay aware of your condition. Watch for fatigue, a failing attitude, distractions, and problems with intra-crew relationships.
Notes: <number>

## Slide 209: Produced by USDA Forest Service Missoula Technology & Development Center
<number>
USDA Forest Service
Missoula Technology & Development Center
Tim Lynch - Project Leader
Mary Trankel - Product Development
Bert Lindler - Editing
Jacob Cowgill - Publishing Assistance
Jim Kautz - Photographic Assistance
Ben Croft - Photographic Assistance
Leslie Anderson - Technical Content Contributor
Chuck Whitlock - Technical Content Contributor
Bill Bickers - Technical Content Contributor
George Jackson - Program Leader
See Table of Contents for additional information resources.
Home
Notes: <number>

## Slide 210: Table of Contents Page 1 of 2
<number>
USDA Forest Service
Missoula Technology & Development Center
Title Page
Overview
Objectives
Introduction
Before Entrapment
  Conditions When Fire Started
  Chronology: July 9
  Chronology: July 10
Between Entrapment & Deployment
Deployment
Questions?
Group Exercise
Lessons Learned
  Intentional Omissions
  Personal Protective Equipment
  Entrapment Avoidance
  Entrapment Reaction
  Fire Shelter Deployment
  Human Factors
    Crew Cohesion
    Fatigue
    Situation Awareness
    Leadership
  Risk Management
    10 Standard Fire Orders
    18 Watchout Situations
    LCES
Home
Next

## Slide 211: Table of Contents Page 2 of 2
<number>
USDA Forest Service
Missoula Technology & Development Center
Training Aids & Information Resources
  Fire Shelters
  Entrapment Avoidance
  Human Factors Training
  Human Factors Workshop Findings & Research
  Crew Cohesion Research
  Incident Response Pocket Guide
  Key Messages from the Forest Service National Leadership Team
  Checklist of Fireline Leadership Responsibilities
  Risk Management Process Checklist
  Last Resort Survival Tips
  Find a Survivable Area
  Pick a Fire Shelter Deployment Site
  What to Expect If You Have to Deploy
Credits
Home
Previous

## Slide 212: Training Aids & Information Resources
<number>
USDA Forest Service
Missoula Technology & Development Center
Incident Response Pocket Guide
  The Operational Leadership Guide on pages iii and iv of the Incident Response Pocket Guide is a checklist of fireline leadership responsibilities.
  Section 1 (in green) of the pocket guide is a comprehensive risk management process checklist.
  New additions to the Risk Management Process section include:
    Safety Zone Guideline (page 7)
    Extended Attack Transition Analysis (page 15)
    Guidelines for How to Properly Refuse Risk (page 17)
    Last Resort Survival Tips (page 18)
Notes: <number>

## Slide 213: Last Resort Survival Tips
<number>
USDA Forest Service
Missoula Technology & Development Center
Incident Response Pocket Guide
  Escape if you can:
  DROP any gear not needed for fire shelter deployment.
  KEEP your fire shelter, hand tool, quart of water, and radio.
  You may be able to use the fire shelter for a heat shield as you move.
  In LIGHT FUELS, you may be able to run through the flames into the black.
  If you are on the flank of the fire, try to get below the fire.
  Consider vehicles or helicopters for escape.
Notes: <number>

## Slide 214: Last Resort Survival Tips
<number>
USDA Forest Service
Missoula Technology & Development Center
Incident Response Pocket Guide
  Find a survivable area:
  Stay out of hazardous terrain features.
  Use bodies of water that are more than 2 feet deep.
  In LIGHT FUELS, you may be able to light an escape fire.
  In other fuels, you may be able to light a backfire.
  Call for helicopter or retardant drops.
  Cut and scatter fuels if there is time.
  Use any available heat barriers, such as structures, large rocks, or dozer berms.
  Consider vehicle traffic hazards on roads.
Notes: <number>

## Slide 215: Last Resort Survival Tips
<number>
USDA Forest Service
Missoula Technology & Development Center
Incident Response Pocket Guide
  Pick a fire shelter deployment site:
  Find the lowest point available.
  Maximize distance from the nearest aerial or heavy fuels.
  Pick a surface that allows the fire shelter to seal, and remove ground fuels.
  Get into the fire shelter before the flame front hits.
  Position your feet toward the fire and hold down the fire shelter.
  Keep your face pressed to the ground.
  Deploy next to each other and keep talking.
Notes: <number>

## Slide 216: Last Resort Survival Tips
<number>
USDA Forest Service
Missoula Technology & Development Center
Incident Response Pocket Guide
  What to Expect:
  Extremely heavy ember showers.
  A superheated air blast to hit before the flame front hits.
  Noise and turbulent powerful winds to hit the fire shelter.
  Pin holes in the fire shelter that allow fire glow inside.
  Heat inside the shelter means there is extreme heat outside.
  Deployments have lasted up to 90 minutes.
  When in doubt, wait it out.
Notes: <number>